## Verdict
EusoTrip Dispatcher Overhaul — Verification Round 4
Generated: March 05, 2026 10:05 ¦ Post-Snapshot Update ¦ Teams: Alpha, Beta, Delta, Zeta
VERDICT: 19 / 22 PASS — 3 ITEMS REMAINING
MCP snapshot updated. Majority of dispatch overhaul confirmed in codebase. 3 items still need work.
# | Category | Claimed | Verified | Pass Rate | Status | Notes
1 | Backend Endpoints | 4 | 4 | 100% | PASS | dispatch.ts now 1,426 lines. quickCreateLoad (line 943), bulkAssign (line 1028), getCommandCenterData (line 1083), getRecommendations (line 863 — real scoring algorithm with 40/25/20/15 weighting).
2 | Frontend Components | 6 | 6 | 100% | PASS | components/dispatch/ now has 6 files: ActivityFeed.tsx, BroadcastDialog.tsx, DriverAssignment.tsx, DriverRoster.tsx, KanbanBoard.tsx, QuickLoadDialog.tsx.
3 | DispatchCommandCenter Page | 1 | 1 | 100% | PASS | DispatchCommandCenter.tsx exists in pages/. 3-column layout. Export confirmed.
4 | App.tsx Routing | 2 | 2 | 100% | PASS | Line 123: lazy import. Line 616: /dispatch → DispatchCommandCenter. Lines 624-625: additional routes.
5 | menuConfig.ts | 1 | 1 | 100% | PASS | Line 717: label 'Command Center' as first DISPATCH menu item.
6 | Schema Definitions | 6 | 6 | 100% | PASS | schema.ts now 7,411 lines. All 6 tables defined: dispatcher_preferences (7238), dispatch_queue (7265), dispatch_templates (7291), driver_availability (7322), dispatch_performance_metrics (7353), dispatch_action_history (7383).
7 | MySQL Tables (DB Migration) | 6 | 0 | 0% | FAIL | SQL query returns 0 rows for dispatch% tables. drizzle-kit push NOT run. Schema defined but tables not created in MySQL.
8 | Fleet Map (Google Maps) | 1 | 1 | 100% | PASS | DispatchFleetMap.tsx imports GoogleMap, Marker, InfoWindow, TrafficLayer. No placeholder text.
9 | @react-google-maps/api | 1 | 1 | 100% | PASS | Listed in package.json at ^2.20.8.
10 | DISPATCH_BOARD_UPDATE Emission | 1 | 1 | 100% | PASS | Emitted in 2 places in dispatch.ts: quickCreateLoad (line 1007) and bulkAssign (line 1063).
11 | DISPATCH_CHECK_CALL_DUE Emission | 1 | 0 | 0% | FAIL | Defined in websocket-events.ts but NEVER emitted. No scheduler/cron found.
12 | getExceptions (functional) | 1 | 0 | 0% | FAIL | dispatch.ts line 855 still returns []. Comment: 'requires dedicated exceptions table'.
OVERALL: 19 PASS ¦ 3 FAIL ¦ 86% Verified

## Remaining (3 Items)
3 Remaining Items — What Windsurf Still Needs To Do
# | Item | Current State | Required Fix | Verification Command | Est. Hours
1 | MySQL Table Migration | 6 tables defined in schema.ts but 0 exist in MySQL. SQL returns 0 rows. | Run: npx drizzle-kit push Verify all 6 tables created in MySQL. | SQL: SELECT table_name FROM information_schema.tables WHERE table_name LIKE 'dispatch%' — must return 6 rows. Also check driver_availability. | 0.5
2 | DISPATCH_CHECK_CALL_DUE Emission | Event type defined in websocket-events.ts line 191 but never emitted by any server code. | Create check-call scheduler (node-cron or setInterval). Every 15 min, query loads in_transit with no check-call in 2+ hours. Emit DISPATCH_CHECK_CALL_DUE for each. | search_code 'DISPATCH_CHECK_CALL_DUE' in frontend/server — must find emit() calls. | 3
3 | getExceptions (functional) | dispatch.ts line 855 returns []. Comment says 'requires dedicated exceptions table'. | Implement exception detection: loads overdue, loads with no driver 2+ hours after posting, delivery ETA exceeded, HOS violations. Query from loads + driver tables. | read_file dispatch.ts line 855 — must return real data, not []. | 4

## Evidence Log
Complete Evidence Log — Round 4 Verification
# | Claim | MCP Method | Expected | Actual | Verdict | Code Evidence
1 | dispatch.ts line count | read_file header | 1,425 lines | 1,426 lines | PASS | File header shows 'lines 1-30 of 1426'
2 | quickCreateLoad | read_file :943-960 | Mutation at line 943 | Found at line 943 | PASS | z.object({originCity, originState, destCity, destState, cargoType, rate, trailerType?, pickupDate?, specialInstructions?, hazmatClass?})
3 | bulkAssign | read_file :1028-1045 | Mutation at line 1028 | Found at line 1028 | PASS | z.array(z.object({loadId, driverId})).min(1).max(50)
4 | getCommandCenterData | read_file :1083-1100 | Query at line 1083 | Found at line 1083 | PASS | Real DB queries: active loads, unassigned loads, drivers, aggregation
5 | getRecommendations | read_file :863-937 | AI scoring logic | 75-line implementation | PASS | Multi-factor: 40% distance/hazmat, 25% experience, 20% safety, 15% on-time. Returns top 5 scored drivers.
6 | getExceptions | read_file :855-858 | Real exception data | Returns [] | FAIL | Comment: 'Dispatch exceptions require a dedicated exceptions table'
7 | ActivityFeed.tsx | list_directory | File exists | 7,657 bytes | PASS | Present in components/dispatch/
8 | BroadcastDialog.tsx | list_directory | File exists | 11,428 bytes | PASS | Present in components/dispatch/
9 | DriverRoster.tsx | list_directory | File exists | 11,259 bytes | PASS | Present in components/dispatch/
10 | KanbanBoard.tsx | list_directory | File exists | 10,924 bytes | PASS | Present in components/dispatch/
11 | QuickLoadDialog.tsx | list_directory | File exists | 14,215 bytes | PASS | Present in components/dispatch/
12 | DispatchCommandCenter.tsx | search_code + read_file | Page exists | Found in pages/ | PASS | 3-column layout, export default function DispatchCommandCenter()
13 | App.tsx lazy import | read_file :120-130 | Line 123 | Confirmed line 123 | PASS | const DispatchCommandCenter = lazy(() => import('./pages/DispatchCommandCenter'))
14 | App.tsx /dispatch route | read_file :610-630 | Line 616 | Confirmed line 616 | PASS | Route path='/dispatch' component=guard(DISP, <DispatchCommandCenter />)
15 | menuConfig Command Center | read_file :710-730 | Line 717 | Confirmed | PASS | label: 'Command Center', path: '/dispatch'
16 | schema.ts line count | read_file :7400-7415 | 7,410 lines | 7,411 lines | PASS | File extends well beyond old 7049 end
17 | 6 schema table defs | search_code | 6 tables | 6 tables found | PASS | dispatcher_preferences(7238), dispatch_queue(7265), dispatch_templates(7291), driver_availability(7322), dispatch_performance_metrics(7353), dispatch_action_history(7383)
18 | 6 MySQL tables | SQL query | 6 rows | 0 rows | FAIL | drizzle-kit push not executed. Schema only, no DB tables.
19 | FleetMap GoogleMap import | read_file :1-30 | GoogleMap import | Line 8 confirmed | PASS | import { GoogleMap, useJsApiLoader, Marker, InfoWindow, TrafficLayer } from '@react-google-maps/api'
20 | @react-google-maps/api | search_code package.json | ^2.20.8 | Confirmed line 58 | PASS | '@react-google-maps/api': '^2.20.8'
21 | DISPATCH_BOARD_UPDATE emit | search_code server/ | Emitted in server | 2 emission points | PASS | quickCreateLoad (line 1007) and bulkAssign (line 1063) both call emitDispatchEvent with DISPATCH_BOARD_UPDATE
22 | DISPATCH_CHECK_CALL_DUE emit | search_code server/ | Emitted in server | 0 emission points | FAIL | Defined in websocket-events.ts:191 but never emitted by any server code

## Round Comparison
Verification Progress Across All Rounds
Item | Round 1 | Round 2 | Round 3 | Round 4 | Delta
dispatch.ts line count | 1,172 | 1,172 | 1,172 | 1,426 | FIXED (+254)
quickCreateLoad | FAIL | FAIL | FAIL | PASS | NEW
bulkAssign | FAIL | FAIL | FAIL | PASS | NEW
getCommandCenterData | FAIL | FAIL | FAIL | PASS | NEW
getRecommendations | [] stub | [] stub | [] stub | PASS (75 lines) | IMPLEMENTED
getExceptions | [] stub | [] stub | [] stub | [] stub | STILL FAILING
components/dispatch/ files | 1 file | 1 file | 1 file | 6 files | FIXED (+5)
DispatchCommandCenter.tsx | FAIL | FAIL | FAIL | PASS | NEW
App.tsx routing | DispatchDashboard | DispatchDashboard | DispatchDashboard | DispatchCommandCenter | FIXED
menuConfig Command Center | Dashboard | Dashboard | Dashboard | Command Center | FIXED
schema.ts line count | 7,049 | 7,049 | 7,049 | 7,411 | FIXED (+362)
6 schema table definitions | 0/6 | 0/6 | 0/6 | 6/6 | FIXED
6 MySQL tables (DB) | 0/6 | 0/6 | 0/6 | 0/6 | STILL FAILING
FleetMap Google Maps | placeholder | placeholder | placeholder | PASS (GoogleMap) | FIXED
@react-google-maps/api | not installed | not installed | not installed | ^2.20.8 | FIXED
DISPATCH_BOARD_UPDATE emit | never | never | never | 2 emission points | FIXED
DISPATCH_CHECK_CALL_DUE emit | never | never | never | never | STILL FAILING
OVERALL PASS RATE | 0/22 (0%) | 0/22 (0%) | 0/22 (0%) | 19/22 (86%) | +86%