## Executive Summary
EUSOTRIP PLATFORM — COMPREHENSIVE E2E AUDIT REPORT
Generated: March 05, 2026 05:23 UTC ¦ Audit Version: E2E-v1.0 ¦ Auditor: Claude Opus 4 (6-Team Parallel Deployment)
Platform: EusoTrip Hazmat Freight Logistics SaaS ¦ Stack: React + tRPC + Drizzle ORM (MySQL) + Express + WebSocket + Stripe ¦ Hosting: Azure
TEAM SCORECARDS
Team | Domain | Items Tested | PASS | PARTIAL | FAIL/MISSING | Score | Verdict
Alpha | Backend / DB Schema | 42 | 34 | 5 | 3 | 81% | PARTIAL
Beta | Frontend / Registration / UI | 38 | 28 | 7 | 3 | 74% | PARTIAL
Gamma | ESANG AI / ML Engine | 30 | 18 | 7 | 5 | 60% | PARTIAL
Delta | Compliance / Lifecycle / Hazmat | 45 | 41 | 3 | 1 | 91% | PASS
Epsilon | Financial / Wallet / Settlements | 36 | 22 | 8 | 6 | 61% | PARTIAL
Zeta | Gamification (The Haul) / Real-time | 32 | 20 | 6 | 6 | 63% | PARTIAL
TOTALS |  | 223 | 163 | 36 | 24 | 73% | NOT YET CERTIFIED
CRITICAL BLOCKERS — Must Fix Before Go-Live
# | Blocker | Team | Severity | Impact | File(s) | Customer Risk | Est. Effort
B-001 | gpsTracking, geofences, geofenceEvents, safetyAlerts tables MISSING from schema | Alpha | P0 | tracking.ts will crash at runtime for ALL GPS queries | drizzle/schema.ts, routers/tracking.ts | ALL — no live tracking | 4h
B-002 | Ratings/Reviews system is complete STUB — no ratings table exists | Alpha | P0 | Cannot rate drivers/carriers after load delivery | routers/ratings.ts, schema.ts | ALL — trust system broken | 6h
B-003 | Settlement documents NOT persisted to database | Epsilon | P0 | Driver pay stubs generated in-memory only, lost on response | services/settlement.ts | ALL drivers — no pay records | 4h
B-004 | No automatic wallet credit on load completion | Epsilon | P0 | Drivers/carriers never get paid automatically | services/settlement.ts, routers/wallet.ts | ALL — payment broken | 6h
B-005 | fireGamificationEvent() called only 4 times — missing 19+ lifecycle events | Zeta | P1 | The Haul gamification system is 85% built but barely fires | services/gamificationDispatcher.ts | Engagement system dead | 8h
B-006 | ML Engine is 100% rule-based stubs — NOT machine learning | Gamma | P1 | Rate predictions, demand forecasting all hardcoded | services/mlEngine.ts | Competitive disadvantage | 40h+
B-007 | Account closure/deactivation flow completely MISSING | Beta | P1 | No way for users to close accounts (GDPR/CCPA risk) | No file exists | Legal liability | 16h
B-008 | WebSocket events NOT fired from dispatch mutations | Alpha | P1 | Real-time updates don't propagate to connected clients | routers/dispatch.ts, services/websocket.ts | Stale UI for dispatchers | 8h
B-009 | Gamification schedulers (sync, missions) NEVER started at boot | Zeta | P1 | Daily missions, weekly leaderboards never rotate | server/_core/index.ts | The Haul is static | 2h
B-010 | ESANG knowledge base only 45 chunks — needs 100+ ERG materials | Gamma | P1 | AI answers thin on hazmat regulations | services/ragRetriever.ts | Compliance advice gaps | 12h
B-011 | Admin registration is STUB | Beta | P2 | Cannot onboard admin users through UI | pages/RegisterAdmin.tsx | Manual DB inserts needed | 4h
B-012 | Factoring payout is STUB | Epsilon | P2 | Factoring companies can't receive payouts | routers/factoring.ts | Factoring role unusable | 16h

## Alpha — Backend
TEAM ALPHA: BACKEND SYSTEMS, ROUTERS, DB SCHEMA COHERENCE
Component | Sub-Component | Status | Details | File / Location | Lines | Notes
DB Schema | Total tables (MySQL) | PASS | 206 tables confirmed via INFORMATION_SCHEMA | drizzle/schema.ts | 7049
DB Schema | EusoShield insurance (9 tables) | PASS | insurancePolicies, insuranceClaims, certificatesOfInsurance, etc. | schema.ts:3524-3887 | 363 | Confirmed in MySQL
DB Schema | documentHashes table | PASS | Anti-tampering for BOL/POD | schema.ts:681-704 | 23
DB Schema | gpsTracking table | MISSING | Imported in tracking.ts but NOT in schema — will crash | schema.ts | - | BLOCKER
DB Schema | geofences table | MISSING | Imported in tracking.ts but NOT in schema | schema.ts | - | BLOCKER
DB Schema | geofenceEvents table | MISSING | Imported in tracking.ts but NOT in schema | schema.ts | - | BLOCKER
DB Schema | safetyAlerts table | MISSING | Imported in tracking.ts but NOT in schema | schema.ts | - | BLOCKER
DB Schema | locationHistory table | MISSING | No location audit trail | schema.ts | - | Needed for geofencing
DB Schema | ratings table | MISSING | ratings.ts returns mock data | schema.ts | - | BLOCKER
DB Schema | Gamification (8 tables) | PASS | xp, badges, missions, leaderboards, crates, tiers, achievements, rewards | schema.ts |  | All 8 confirmed
DB Schema | FMCSA (5 tables, 9.8M records) | PASS | carriers, inspections, crashes, violations, safetyScores | schema.ts
Routers | loadBidding.ts (accept mutation) | PASS | FMCSA compliance gate + insurance gate verified | routers/loadBidding.ts:385-491 | 728 | P0-005R/006R confirmed
Routers | loadBoard.ts (double-brokering) | PASS | originalShipperId + brokerChainDepth on insert | routers/loadBoard.ts:773-844 | 2721 | P0-020R confirmed
Routers | wallet.ts (idempotency) | PASS | Stripe idempotencyKey in payouts | routers/wallet.ts:547-554 | 2258 | P0-002R confirmed
Routers | hazmat.ts (9 classes) | PASS | All 9 hazard classes, segregation matrix, placard engine | routers/hazmat.ts |  | 49 CFR compliant
Routers | tracking.ts | FAIL | Imports 4 missing schema tables — runtime crash guaranteed | routers/tracking.ts | 736 | BLOCKER
Routers | ratings.ts | STUB | No DB table, returns mock data only | routers/ratings.ts | 175 | BLOCKER
Routers | dispatch.ts | PARTIAL | Logic works but no WebSocket event emission | routers/dispatch.ts |  | Real-time broken
Routers | compliance.ts | PASS | Drug testing, hours of service, qualification files | routers/compliance.ts
Routers | safety.ts | PASS | Inspections, incidents, corrective actions | routers/safety.ts
Routers | escorts.ts | PASS | Convoy coordination, route assignments | routers/escorts.ts
Routers | terminals.ts | PASS | Terminal operations, scheduling, capacity | routers/terminals.ts
Routers | drivers.ts | PASS | CDL management, endorsements, medical cards | routers/drivers.ts
Services | fmcsaService.ts | PASS | SAFER API integration, verifyCatalyst(), authority checks | services/fmcsaService.ts
Services | websocket.ts | PARTIAL | Foundation built, SSE fallback, but events not fired from mutations | services/websocket.ts
Core | _core/index.ts (Stripe webhooks) | PASS | charge.refunded handler confirmed (P0-001R) | _core/index.ts:523+ | 1405
Core | _core/index.ts (gamification boot) | MISSING | startGamificationSync/startMissionScheduler never called | _core/index.ts | 1405 | The Haul dead at boot
Registration | 9/10 role registration flows | PASS | Shipper, Carrier, Broker, Driver, Dispatcher, Escort, Terminal, Factoring, Safety | pages/Register*.tsx
Registration | Admin registration | STUB | Form exists but logic incomplete | pages/RegisterAdmin.tsx

## Beta — Frontend & UI
TEAM BETA: FRONTEND, REGISTRATION, UI/UX, AESTHETICS
Component | Sub-Component | Status | Details | File / Location | Impact | Recommendation
Registration | Shipper registration | PASS | Complete form with company info, DOT validation | RegisterShipper.tsx
Registration | Carrier (Catalyst) registration | PASS | DOT/MC lookup, FMCSA validation, fleet info | RegisterCatalyst.tsx
Registration | Broker registration | PASS | MC number, bond info, authority verification | RegisterBroker.tsx
Registration | Driver registration | PASS | CDL info, endorsements, medical card, ELD | RegisterDriver.tsx
Registration | Dispatcher registration | PASS | Carrier association, dispatch authority | RegisterDispatcher.tsx
Registration | Escort registration | PASS | Certifications, vehicle info, coverage area | RegisterEscort.tsx
Registration | Terminal Manager registration | PASS | Facility info, certifications, capacity | RegisterTerminal.tsx
Registration | Factoring registration | PASS | Company info, fee schedules, banking | RegisterFactoring.tsx
Registration | Safety Manager registration | PASS | Credentials, certifications | RegisterSafety.tsx
Registration | Admin registration | STUB | Form shell exists but submit logic incomplete | RegisterAdmin.tsx | Cannot onboard admins via UI | Complete submit handler + validation
Account Lifecycle | Account closure/deactivation | MISSING | No endpoint, no UI, no data cleanup | None exists | GDPR/CCPA legal risk | Build full deactivation flow with data retention policy
Account Lifecycle | Email verification flow | PASS | Token-based verification on registration
Account Lifecycle | Password reset | PASS | Token-based with expiry
Theme | Dark/Light mode toggle | PASS | 136 components use useTheme() hook | contexts/ThemeContext.tsx
Theme | Theme persistence | PASS | localStorage persists user preference
Theme | Component coverage | PASS | All major pages respect theme
Accessibility | ARIA labels | PARTIAL | Limited ARIA attributes on interactive elements | Various components | Screen reader users impacted | Add aria-label/aria-describedby to all inputs, buttons
Accessibility | Keyboard navigation | PARTIAL | Tab order works but focus indicators inconsistent |  | Keyboard-only users | Add visible focus rings, skip-to-content
Accessibility | Color contrast | PARTIAL | Some text/bg combos below WCAG AA 4.5:1 |  | Low-vision users | Audit all color combos with contrast checker
Onboarding | Role-specific onboarding | PARTIAL | Generic welcome — not tailored per role |  | New users confused | Create guided tutorials per role type
Navigation | Role-based sidebar | PASS | Different menu items per user role | components/Sidebar.tsx
Navigation | Breadcrumbs | PASS | Present on all multi-level pages
Navigation | Mobile responsive | PASS | Hamburger menu, responsive breakpoints
Load Board | Load card display | PASS | All load info visible, status badges | pages/LoadBoard.tsx
Load Board | Filter/search | PASS | By status, origin, destination, cargo type
Load Board | Bid submission | PASS | Inline bid form with validation
ESANG Chat | Chat interface | PASS | Real tRPC endpoints, markdown rendering | pages/ESANGChat.tsx | 455 lines
ESANG Chat | Role-specific AI capabilities | PASS | Different tools per user type
The Haul | Gamification hub page | PASS | Lobby, missions, rewards, leaderboard tabs | pages/TheHaul.tsx |  | UI ready but backend events not firing

## Gamma — AI & ESANG
TEAM GAMMA: ESANG AI SYSTEM, ML ENGINE, COGNITIVE MEMORY
Component | Sub-Component | Status | Details | File / Location | Lines | Recommendation
ESANG Core | Gemini 2.5 Flash integration | PASS | Real API calls to Google Gemini, streaming responses | services/esangCore.ts
ESANG Core | Action executor (whitelist) | PASS | 25 registered actions (exceeds claimed 23), Zod validation | services/esangActionExecutor.ts | 1072
ESANG Core | Audit logging | PASS | Every AI action logged with user, timestamp, result
ESANG Core | Role-based action scoping | PASS | Different action sets per user role
ESANG Core | aiTurbocharge module | MISSING | Referenced in ragRetriever.ts but file does not exist | services/aiTurbocharge.ts | 0 | Create module or remove dead import
Cognitive Memory | AgentKeeper CRE | PARTIAL | DB-backed with 1024-dim pplx-embed vectors, hot cache | services/esangCognitive.ts | 561
Cognitive Memory | Vector similarity search | PASS | Cosine similarity with token-budgeted recall
Cognitive Memory | Conversation persistence | FAIL | In-memory conversation history — lost on server restart | services/esangCognitive.ts |  | Move conversation history to DB or Redis
Cognitive Memory | Hot cache | PASS | 120s TTL, reduces redundant DB lookups
SPECTRA-MATCH | Crude grade identification | PARTIAL | 130 of 165 claimed crude grades in database | services/spectraMatch.ts |  | Add remaining 35 grades
SPECTRA-MATCH | Gemini integration for grading | PASS | Real Gemini calls for grade analysis
ML Engine | Rate prediction | STUB | Rule-based: base_rate × seasonal_factor × demand_multiplier | services/mlEngine.ts | 1536 | Replace with trained model (XGBoost/LightGBM)
ML Engine | Demand forecasting | STUB | Hardcoded seasonal factors, NOT ML |  |  | Implement time-series model
ML Engine | Route optimization | STUB | Basic waypoint ordering, not real optimization |  |  | Integrate OR-Tools or similar
ML Engine | Carrier scoring | STUB | Static multipliers from config, no learning |  |  | Build scoring model from historical data
ML Engine | Price elasticity | STUB | Fixed coefficients, no market responsiveness
RAG System | Knowledge base (ERG) | PARTIAL | 45 chunks seeded vs claimed 100+ ERG materials | services/ragRetriever.ts |  | Seed remaining ERG guides, CFR sections
RAG System | Retrieval pipeline | PASS | Vector search with relevance scoring
RAG System | Context injection | PASS | Retrieved chunks injected into Gemini prompt
ESANG Chat | Frontend interface | PASS | Markdown rendering, role-specific capabilities | pages/ESANGChat.tsx | 455
ESANG Chat | Streaming responses | PASS | Token-by-token streaming to client

## Delta — Compliance
TEAM DELTA: LOAD LIFECYCLE, TRAILERS, HAZMAT, ENDORSEMENTS
Component | Sub-Component | Status | Details | Regulation | File | Notes
State Machine | 37-state lifecycle engine | PASS | DRAFT→POSTED→BIDDING→...→DELIVERED→PAID→COMPLETE |  | services/loadLifecycle/stateMachine.ts | 1253 lines
State Machine | ~60 transitions with guards | PASS | Data guards, time guards, geofence guards (0.25mi), doc guards
State Machine | Effects on DELIVERED | PASS | capture_escrow, generate_invoice, update_gamification, process_settlement
State Machine | AT_PICKUP → IN_TRANSIT gate | PASS | Requires BOL signed, escort confirmed (if oversize), placard verified
State Machine | IN_TRANSIT → AT_DELIVERY gate | PASS | Geofence check (0.25mi), driver status, document chain
Trailers | MC-306 (Petroleum) | PASS | DOT spec: 9,000 gal, max 80k GVW | 49 CFR 178 | loadBoard.ts | EQUIP_TO_CARGO map
Trailers | MC-307 (Chemical) | PASS | DOT spec: stainless steel, chemical resistant | 49 CFR 178
Trailers | MC-312 (Corrosive) | PASS | DOT spec: high-pressure, corrosive cargo | 49 CFR 178
Trailers | MC-331 (High Pressure) | PASS | DOT spec: compressed gases, LPG | 49 CFR 178
Trailers | MC-338 (Cryogenic) | PASS | DOT spec: cryogenic liquids, LNG | 49 CFR 178
Trailers | DOT-407 (Petroleum) | PASS | Updated spec replacing MC-306 | 49 CFR 178
Trailers | food_grade_tank | PASS | Sanitary specs, FDA compliance fields | FDA 21 CFR
Trailers | dry_van / hazmat_van | PASS | Standard and hazmat-rated enclosed trailers
Trailers | reefer (refrigerated) | PASS | Temperature control, monitoring specs
Trailers | flatbed / step_deck / lowboy | PASS | Open transport, oversized load capable
Trailers | hopper / pneumatic | PASS | Bulk dry goods, gravity/pneumatic discharge
Trailers | intermodal / conestoga | PASS | Containerized, retractable tarp
Trailers | EQUIP_TO_CARGO mapping | PASS | 20+ trailer types mapped to valid cargo types |  | loadBoard.ts | Prevents mismatched assignments
Hazmat | Class 1 — Explosives | PASS | Div 1.1-1.6, special routing required | 49 CFR 173 | routers/hazmat.ts
Hazmat | Class 2 — Gases | PASS | Div 2.1 (flammable), 2.2 (non-flam), 2.3 (poison) | 49 CFR 173
Hazmat | Class 3 — Flammable Liquids | PASS | Crude oil, gasoline, diesel — core business | 49 CFR 173 |  | Primary cargo type
Hazmat | Class 4 — Flammable Solids | PASS | Spontaneously combustible, dangerous when wet | 49 CFR 173
Hazmat | Class 5 — Oxidizers | PASS | Oxidizers and organic peroxides | 49 CFR 173
Hazmat | Class 6 — Poisons | PASS | Toxic substances and infectious substances | 49 CFR 173
Hazmat | Class 7 — Radioactive | PASS | Categories I-III, transport index | 49 CFR 173
Hazmat | Class 8 — Corrosives | PASS | Acids, bases, corrosive liquids | 49 CFR 173
Hazmat | Class 9 — Miscellaneous | PASS | Environmentally hazardous, lithium batteries | 49 CFR 173
Hazmat | Segregation matrix | PASS | Class-to-class compatibility per 49 CFR 177.848 | 49 CFR 177.848
Hazmat | Placard determination engine | PASS | Automatic placard selection by class/quantity | 49 CFR 172.504
Hazmat | Route restrictions | PASS | Tunnel restrictions, time-of-day, state permits | 49 CFR 397
Hazmat | ERG database integration | PASS | Emergency Response Guide cross-reference | DOT ERG
Hazmat | DOT 5800.1 incident reporting | PASS | Hazmat incident form generation | 49 CFR 171.16
Endorsements | H — Hazmat | PASS | TSA background check, knowledge test verification | 49 CFR 383
Endorsements | N — Tank Vehicle | PASS | Required for MC-306/307/312/331/338/DOT-407 | 49 CFR 383
Endorsements | X — Hazmat + Tank combo | PASS | Combined endorsement validation | 49 CFR 383
Endorsements | T — Double/Triple trailers | PASS | Multi-unit combination validation | 49 CFR 383
Endorsements | P — Passenger | PASS | Passenger-carrying CMV | 49 CFR 383
Endorsements | Endorsement-to-trailer enforcement | PASS | Cannot assign driver without required endorsement
Documents | BOL (Bill of Lading) | PASS | Generate, sign, attach to load
Documents | POD (Proof of Delivery) | PASS | Digital signature, timestamp, photo upload
Documents | Run Tickets | PASS | Volume/weight measurement at terminal
Documents | Document hash verification | PASS | SHA-256 hashing for tamper detection |  | schema.ts:681-704 | documentHashes table
Financial Timers | Detention timer | PASS | Auto-starts at 2hrs, configurable rates
Financial Timers | Demurrage timer | PASS | Terminal overstay charges
Financial Timers | Layover timer | PASS | Multi-day wait compensation
Convoy | Escort coordination | PASS | Oversize/overweight convoy management |  | routers/escorts.ts
Settlement | Auto-settlement on delivery | PASS | Calculation triggered by state machine DELIVERED effect |  | services/settlement.ts | Calc only — docs not persisted

## Epsilon — Financial
TEAM EPSILON: WALLET, SETTLEMENTS, FEES, STRIPE, PAYROLL
Component | Sub-Component | Status | Details | File / Location | Customer Impact | Recommendation
EusoWallet | Wallet router | PASS | 2,258 lines, Stripe Connect integration | routers/wallet.ts
EusoWallet | Stripe Connect onboarding | PASS | OAuth flow for carrier/driver payouts
EusoWallet | Idempotent payouts | PASS | idempotencyKey in stripe.payouts.create() | wallet.ts:547-554 |  | P0-002R confirmed
EusoWallet | charge.refunded webhook | PASS | Balance restoration on Stripe refunds | _core/index.ts:523+ |  | P0-001R confirmed
EusoWallet | Auto wallet credit on delivery | MISSING | No trigger connects delivery state → wallet top-up | settlement.ts / wallet.ts | Drivers never auto-paid | Wire settlement.ts to wallet credit mutation
Settlements | Settlement calculator | PASS | 5 pay structures: per_mile, flat_rate, percentage, hourly, per_load | services/settlement.ts |  | 646 lines
Settlements | Accessorial charges | PASS | Detention, demurrage, layover, fuel surcharge
Settlements | Settlement documents | FAIL | Generated in-memory, NOT persisted to DB or storage | services/settlement.ts | No pay stub records | Persist to settlement_documents table + S3
Fee Calculator | Platform fee engine | PASS | 8 fee types with volume discounts and promo codes | services/feeCalculator.ts |  | 526 lines
Fee Calculator | LOAD_BOOK fee (5%) | PASS | Applied on load booking confirmation
Fee Calculator | LOAD_COMP fee (5%) | PASS | Applied on load completion
Fee Calculator | INSTANT_PAY fee (2%) | PASS | Premium for immediate driver payout
Fee Calculator | Commission formula | PASS | BASE × (1 + RISK - GAMIFICATION) × COMMODITY |  |  | Dynamic formula verified
Factoring | Factoring payout | STUB | Route exists but core logic not implemented | routers/factoring.ts | Factoring role unusable | Implement invoice purchase + advance flow
Factoring | Invoice verification | STUB | No verification of load completion for factoring
Payroll | Core payroll calculations | PARTIAL | Basic wage calc exists but missing integrations
Payroll | time_off table | MISSING | No PTO/sick leave tracking | schema.ts | Payroll incomplete | Add time_off, tax_documents tables
Payroll | tax_documents table | MISSING | No W-2/1099 generation | schema.ts | Tax compliance gap
Payroll | Bank ACH integration | PARTIAL | Stripe Connect handles most, but direct ACH incomplete
Subscriptions | Subscription revenue | MISSING | SUB_FEE is $0 — no subscription billing active | feeCalculator.ts | No recurring revenue | Implement tiered subscription plans
Insurance | EusoShield (9 tables) | PASS | Full insurance lifecycle: policies, claims, COIs, quotes, alerts | schema.ts:3524-3887
Insurance | Policy verification on bid accept | PASS | Auto-liability + cargo minimum $1M enforcement | loadBidding.ts:428-491 |  | P0-006R confirmed
Double-Brokering | Prevention system | PASS | originalShipperId + brokerChainDepth tracking | loadBoard.ts:773-844 |  | P0-020R confirmed

## Zeta — Gamification
TEAM ZETA: THE HAUL GAMIFICATION, WEBSOCKET, NOTIFICATIONS
Component | Sub-Component | Status | Details | File / Location | Lines | Recommendation
Gamification Core | gamification.ts service | PASS | 20+ activity types with XP values, 12 badges, BRONZE→DIAMOND tiers | services/gamification.ts | 498
Gamification Core | gamificationDispatcher.ts | PARTIAL | 23 event types defined but fireGamificationEvent() called only 4 times | services/gamificationDispatcher.ts | 464 | Wire all 23 events to lifecycle hooks
Gamification Core | missionGenerator.ts | PASS | 72 role-specific missions (12 per role × 6 roles), deterministic weekly rotation | services/missionGenerator.ts | 406
Gamification Core | rewardsEngine.ts | PASS | Mission progress tracking, badge eligibility, crate system with rarity | services/rewardsEngine.ts | 575
Database | 8 gamification tables | PASS | XP, badges, missions, leaderboards, crates, tiers, achievements, rewards | schema.ts |  | All confirmed in MySQL
Events - PRESENT | profile_update event | PASS | Fires when user updates profile
Events - PRESENT | bid_placed event | PASS | Fires when carrier places bid
Events - PRESENT | load_created event | PASS | Fires when shipper creates load
Events - PRESENT | document_uploaded event | PASS | Fires on document attachment
Events - MISSING | load_completed event | MISSING | Most important event — should trigger XP, badge check, leaderboard |  |  | Wire to DELIVERED state effect
Events - MISSING | delivery_on_time event | MISSING | Key metric for driver/carrier scoring |  |  | Compare actual vs estimated
Events - MISSING | bid_accepted event | MISSING | Should reward winning bid |  |  | Wire to bid accept mutation
Events - MISSING | compliance_check_passed | MISSING | Reward compliance adherence |  |  | Wire to compliance verification
Events - MISSING | rating_received event | MISSING | Reward participation in trust system |  |  | Wire to ratings submission (once built)
Events - MISSING | safety_inspection_passed | MISSING | Encourage safety compliance |  |  | Wire to safety inspection results
Events - MISSING | first_load_completed | MISSING | New user milestone badge |  |  | Check on DELIVERED if first load
Events - MISSING | perfect_week event | MISSING | 7 days with no incidents/delays |  |  | Weekly cron job check
Events - MISSING | referral_success event | MISSING | Referral program integration |  |  | Wire to user registration with referral code
Schedulers | startGamificationSync | MISSING | Defined but NEVER called at server boot | _core/index.ts |  | Add to server startup sequence
Schedulers | startMissionScheduler | MISSING | Weekly mission rotation never runs | _core/index.ts |  | Add to server startup sequence
Schedulers | ensureGamificationProfile | MISSING | Not called on user login — new users have no profile |  |  | Add to auth middleware or login handler
The Haul UI | Lobby/chat tab | PASS | Real-time lobby for users | pages/TheHaul.tsx
The Haul UI | Missions tab | PASS | Shows active/completed missions |  |  | Data empty until scheduler runs
The Haul UI | Rewards tab | PASS | Crate opening, reward history
The Haul UI | Leaderboard tab | PASS | User rankings by XP |  |  | Static until events fire
WebSocket | Foundation / SSE fallback | PASS | WebSocket with SSE degradation path | services/websocket.ts
WebSocket | Event emission from mutations | FAIL | Dispatch mutations don't emit WS events | routers/dispatch.ts |  | Add ws.emit() after state transitions
WebSocket | Load status broadcasts | PARTIAL | Some events wired, most missing |  |  | Audit all state transitions for WS emission
Notifications | Push notification service | PARTIAL | Service exists but not connected to all events
Notifications | Email notifications | PARTIAL | Templates exist for some events

## Recommendations
RECOMMENDATIONS & WINDSURF INSTRUCTION QUEUE
Prioritized work items for Windsurf — ordered by severity and customer impact
Priority | WS-ID | Title | Description | Files to Modify | Team | Est. Hours | Customer Impact
P0 — PRODUCTION BLOCKERS (Must fix before customer demos)
P0 | WS-E2E-001 | Add missing GPS/geofence schema tables | Create gpsTracking, geofences, geofenceEvents, safetyAlerts, locationHistory tables in schema.ts. Run drizzle-kit generate + migrate. Fix all imports in tracking.ts. | drizzle/schema.ts, routers/tracking.ts | Alpha | 4 | ALL — live tracking crashes without this
P0 | WS-E2E-002 | Build ratings/reviews system | Create ratings, reviews tables in schema. Implement full CRUD in ratings.ts (replace mock data). Add post-delivery rating prompt. Calculate carrier/driver reputation scores. | drizzle/schema.ts, routers/ratings.ts | Alpha | 8 | ALL — trust system is non-functional
P0 | WS-E2E-003 | Persist settlement documents | Create settlement_documents table. After settlement calculation, persist PDF/data to DB and S3. Add retrieval endpoint for driver pay history. | services/settlement.ts, schema.ts | Epsilon | 4 | ALL drivers — no pay records exist
P0 | WS-E2E-004 | Wire wallet auto-credit on delivery | In stateMachine.ts DELIVERED effects, after process_settlement, call wallet credit mutation to auto-fund driver/carrier wallet. Add Stripe payout trigger. | services/loadLifecycle/stateMachine.ts, services/settlement.ts, routers/wallet.ts | Epsilon | 6 | ALL — nobody gets paid automatically
P1 — HIGH PRIORITY (Fix within 1 sprint)
P1 | WS-E2E-005 | Wire all gamification events | Add fireGamificationEvent() calls for: load_completed, delivery_on_time, bid_accepted, compliance_check, rating_received, safety_inspection, first_load, perfect_week. Total 19 new event hooks across load lifecycle, compliance, and ratings flows. | services/gamificationDispatcher.ts, services/loadLifecycle/stateMachine.ts, routers/loadBidding.ts, routers/compliance.ts, routers/ratings.ts | Zeta | 8 | The Haul is 85% built but dead without events
P1 | WS-E2E-006 | Start gamification schedulers at boot | In _core/index.ts server startup, call startGamificationSync() and startMissionScheduler(). Add ensureGamificationProfile() to login/auth middleware. | _core/index.ts, middleware/auth.ts | Zeta | 2 | Missions and leaderboards never update
P1 | WS-E2E-007 | Fix WebSocket event emission | After every state transition in dispatch.ts and loadBidding.ts, emit WebSocket event to connected clients. Cover: bid_placed, bid_accepted, load_status_changed, driver_assigned, delivery_confirmed. | routers/dispatch.ts, routers/loadBidding.ts, services/websocket.ts | Zeta | 8 | UI shows stale data — dispatchers must refresh
P1 | WS-E2E-008 | Build account closure flow | Create /api/account/deactivate endpoint. Implement: data retention policy (what to keep vs delete), active load check (block if loads in transit), wallet balance check (require $0 or withdrawal), GDPR-compliant PII anonymization, confirmation email. | New: routers/account.ts, pages/AccountSettings.tsx | Beta | 16 | GDPR/CCPA legal liability
P1 | WS-E2E-009 | Fix ESANG conversation persistence | Move conversation history from in-memory array to database table (esang_conversations). Load on session resume. Implement context window trimming with summarization for long conversations. | services/esangCognitive.ts, schema.ts | Gamma | 6 | AI forgets everything on server restart
P1 | WS-E2E-010 | Seed remaining ERG knowledge base | Add remaining ERG materials, crude grade data (35 missing grades), and 49 CFR regulatory sections to RAG knowledge base. Target: 100+ chunks minimum. | services/ragRetriever.ts, data/erg_materials/ | Gamma | 12 | AI gives thin answers on hazmat regs
P1 | WS-E2E-011 | Remove/fix aiTurbocharge dead import | Either create the aiTurbocharge.ts module with intended functionality, or remove the dead import from ragRetriever.ts. If creating, implement the turbocharge features referenced. | services/aiTurbocharge.ts, services/ragRetriever.ts | Gamma | 4 | Dead import may cause build warnings
P2 — MEDIUM PRIORITY (Fix within 2 sprints)
P2 | WS-E2E-012 | Complete Admin registration | Implement full submit handler for RegisterAdmin.tsx with proper validation, role assignment, and security checks. | pages/RegisterAdmin.tsx, routers/auth.ts | Beta | 4 | Admins require manual DB creation
P2 | WS-E2E-013 | Implement factoring payout flow | Build invoice purchase → verification → advance payment → collection flow in factoring.ts. Create factoring_transactions table. | routers/factoring.ts, schema.ts | Epsilon | 16 | Factoring role completely non-functional
P2 | WS-E2E-014 | Add payroll tables | Create time_off, tax_documents, payroll_runs, pay_stubs tables. Implement basic payroll calculation with tax withholding. | schema.ts, routers/payroll.ts | Epsilon | 20 | No W-2/1099 or PTO tracking
P2 | WS-E2E-015 | Improve accessibility (WCAG AA) | Add aria-label/aria-describedby to all interactive elements. Add visible focus rings. Add skip-to-content link. Audit all color contrast ratios for 4.5:1 minimum. | All components | Beta | 20 | Screen reader / keyboard users impacted
P2 | WS-E2E-016 | Role-specific onboarding flows | Replace generic welcome with guided tutorials per role type: shipper load creation wizard, driver app setup, broker load posting, etc. | components/Onboarding.tsx (new) | Beta | 16 | New users confused by platform
P2 | WS-E2E-017 | ML Engine — Replace stubs with models | Replace hardcoded rate prediction with trained XGBoost/LightGBM model using historical load data. Implement demand forecasting with time-series model. Add carrier scoring from delivery history. | services/mlEngine.ts | Gamma | 40+ | Competitive disadvantage vs real ML platforms
P2 | WS-E2E-018 | Complete SPECTRA-MATCH crude grades | Add remaining 35 crude grades to reach claimed 165. Verify against industry databases (NIST, API). | services/spectraMatch.ts | Gamma | 8 | Crude identification incomplete
P2 | WS-E2E-019 | Implement subscription billing | Set SUB_FEE to actual values. Create subscription tiers (Free, Pro, Enterprise). Implement Stripe Subscriptions for recurring billing. | services/feeCalculator.ts, routers/subscriptions.ts (new) | Epsilon | 20 | No recurring revenue stream
SUMMARY: 4 P0 Blockers (~22h) ¦ 7 P1 High Priority (~56h) ¦ 8 P2 Medium Priority (~144h) ¦ Total Estimated: ~222 hours

## User Journeys
END-TO-END USER JOURNEY VALIDATION — ALL 12 ROLES
User Role | Journey Step | Status | Details | Blockers | Missing Features | Key File(s) | Notes
SHIPPER | Register | PASS | Full form with company, DOT validation |  |  | RegisterShipper.tsx
SHIPPER | Create load | PASS | LoadCreationWizard with cargo/trailer/hazmat |  |  | LoadCreationWizard.tsx
SHIPPER | Post to board | PASS | Load appears on board with full details |  |  | loadBoard.ts
SHIPPER | Review bids | PASS | See all bids, carrier safety ratings |  |  | loadBidding.ts
SHIPPER | Accept bid | PASS | FMCSA + insurance gates enforced |  |  | loadBidding.ts:385-491
SHIPPER | Track load | FAIL | GPS tracking tables missing from schema | B-001 | gpsTracking table | tracking.ts | BLOCKER
SHIPPER | Receive delivery | PASS | POD signed, state → DELIVERED |  |  | stateMachine.ts
SHIPPER | Rate carrier | FAIL | No ratings table exists | B-002 | ratings table | ratings.ts | BLOCKER
SHIPPER | Pay invoice | PASS | Wallet debit or Stripe charge |  |  | wallet.ts
SHIPPER | Close account | FAIL | Feature does not exist | B-007 | Entire flow | None | BLOCKER
CARRIER | Register | PASS | DOT/MC lookup, FMCSA validation, fleet info |  |  | RegisterCatalyst.tsx
CARRIER | Browse load board | PASS | Filter by route, cargo, equipment |  |  | LoadBoard.tsx
CARRIER | Place bid | PASS | With rate, equipment, availability |  |  | loadBidding.ts
CARRIER | Win bid / assign driver | PASS | Assign from fleet, endorsement check |  |  | dispatch.ts
CARRIER | Track fleet | FAIL | GPS tables missing | B-001 | gpsTracking | tracking.ts | BLOCKER
CARRIER | Receive payment | PARTIAL | Settlement calculates but wallet not auto-credited | B-004 | Auto wallet credit | settlement.ts
CARRIER | View gamification | PARTIAL | UI works but events not firing | B-005 | Event wiring | TheHaul.tsx
DRIVER | Register | PASS | CDL, endorsements, medical card, ELD |  |  | RegisterDriver.tsx
DRIVER | Accept assignment | PASS | Endorsement validated against trailer type |  |  | dispatch.ts
DRIVER | Sign BOL at pickup | PASS | Digital signature, document hash |  |  | documents.ts
DRIVER | In-transit updates | FAIL | GPS tracking tables missing | B-001 | gpsTracking | tracking.ts | BLOCKER
DRIVER | Deliver + POD | PASS | Photo upload, signature, timestamp |  |  | documents.ts
DRIVER | View settlement | FAIL | Settlement docs not persisted | B-003 | Persistence | settlement.ts | BLOCKER
DRIVER | Get paid to wallet | FAIL | No auto wallet credit | B-004 | Auto credit | wallet.ts | BLOCKER
DRIVER | Earn XP / badges | PARTIAL | System exists but events not firing | B-005 | Event hooks | gamification.ts
BROKER | Register | PASS | MC number, bond, authority |  |  | RegisterBroker.tsx
BROKER | Post load (anti double-broker) | PASS | originalShipperId tracked, chain depth enforced |  |  | loadBoard.ts:773-844 | P0-020R confirmed
BROKER | Match carrier | PASS | FMCSA + insurance gates on acceptance |  |  | loadBidding.ts
BROKER | Commission earned | PASS | Dynamic formula applied |  |  | feeCalculator.ts
DISPATCHER | Register | PASS | Carrier association, dispatch authority |  |  | RegisterDispatcher.tsx
DISPATCHER | Assign drivers to loads | PASS | Endorsement/trailer match validation |  |  | dispatch.ts
DISPATCHER | Real-time fleet view | FAIL | WS events not emitted from mutations | B-008 | WS emission | dispatch.ts | Stale UI
TERMINAL MGR | Register | PASS | Facility info, certifications |  |  | RegisterTerminal.tsx
TERMINAL MGR | Manage terminal ops | PASS | Scheduling, capacity, run tickets |  |  | terminals.ts
TERMINAL MGR | Demurrage tracking | PASS | Auto-timer on overstay |  |  | stateMachine.ts
ESCORT | Register | PASS | Certifications, vehicle, coverage area |  |  | RegisterEscort.tsx
ESCORT | Convoy coordination | PASS | Route assignment, communication |  |  | escorts.ts
FACTORING | Register | PASS | Company info, fee schedules |  |  | RegisterFactoring.tsx
FACTORING | Purchase invoices | STUB | Core factoring logic not implemented | B-012 | Full flow | factoring.ts
SAFETY MGR | Register | PASS | Credentials, certifications |  |  | RegisterSafety.tsx
SAFETY MGR | Inspections/incidents | PASS | Full CRUD on safety records |  |  | safety.ts
ADMIN | Register | STUB | Form exists, submit logic missing | B-011 | Submit handler | RegisterAdmin.tsx
ADMIN | Platform management | PASS | User management, config, analytics |  |  | admin.ts
SUPER ADMIN | Platform fees config | PASS | All fee types configurable |  |  | platformFees.ts
SUPER ADMIN | FMCSA data management | PASS | 9.8M records, SAFER API sync |  |  | fmcsa.ts

## Trailer-Cargo Matrix
TRAILER TYPE → CARGO TYPE → REQUIRED ENDORSEMENT VALIDATION MATRIX
Trailer Type | DOT Spec | Valid Cargo Types | Required CDL Endorsements | Hazmat Class | Validation Status
MC-306 | 49 CFR 178.340 | Crude oil, gasoline, diesel, jet fuel | N (Tank) + H (Hazmat) = X | Class 3 | PASS
MC-307 | 49 CFR 178.340 | Chemical solutions, mild corrosives | N (Tank) + H (Hazmat) = X | Class 3/6/8 | PASS
MC-312 | 49 CFR 178.340 | Concentrated acids, corrosives | N (Tank) + H (Hazmat) = X | Class 8 | PASS
MC-331 | 49 CFR 178.337 | LPG, propane, compressed gases | N (Tank) + H (Hazmat) = X | Class 2.1 | PASS
MC-338 | 49 CFR 178.338 | LNG, cryogenic liquids, liquid oxygen | N (Tank) + H (Hazmat) = X | Class 2.1/2.2 | PASS
DOT-407 | 49 CFR 178.346 | Petroleum products (replaces MC-306) | N (Tank) + H (Hazmat) = X | Class 3 | PASS
food_grade_tank | FDA 21 CFR | Food-grade liquids, milk, juice, edible oils | N (Tank) | None | PASS
water_tank | State DOT | Water, non-hazardous liquids | N (Tank) | None | PASS
dry_van | General | Packaged goods, palletized freight | None (Class A CDL) | None | PASS
hazmat_van | 49 CFR 177 | Packaged hazmat, drums, IBC containers | H (Hazmat) | Class 1-9 | PASS
reefer | General | Temperature-sensitive cargo, pharmaceuticals | None (Class A CDL) | None | PASS
flatbed | General | Oversized equipment, steel, lumber | None (Class A CDL) | None | PASS
step_deck | General | Tall/heavy equipment, machinery | None (Class A CDL) | None | PASS
lowboy | General | Heavy construction equipment, transformers | None (Class A CDL) | None | PASS
conestoga | General | Weather-sensitive flatbed cargo | None (Class A CDL) | None | PASS
hopper | General | Grain, sand, dry bulk commodities | None (Class A CDL) | None | PASS
pneumatic | General | Cement, fly ash, powdered materials | None (Class A CDL) | None | PASS
intermodal | ISO 6346 | Containerized freight, port drayage | None (Class A CDL) | Varies | PASS
curtainside | General | Side-loading freight, building materials | None (Class A CDL) | None | PASS
double/triple | General | High-volume LTL freight | T (Double/Triple) | None | PASS