## Post-Windsurf Audit
EUSOTRIP — POST-WINDSURF COMPLETION AUDIT
All 6 Teams ¦ March 5, 2026 ¦ Windsurf Claims: DONE ¦ Actual: 35% DONE
P0 ID | Task | Team | Previous Status | Current Status | Evidence Summary | Critical Notes | Verdict
WS-P0-001 | Stripe Webhooks | Epsilon | DONE | PARTIAL | 20+ events handled; constructEvent verified | charge.refunded handler STILL MISSING | NEEDS WORK
WS-P0-002 | Payout Execution | Epsilon | DONE | PARTIAL | stripe.payouts.create() exists | Zero idempotency key — duplicate payout risk | NEEDS WORK
WS-P0-003 | Fee Config Seeding | Epsilon | NOT DONE | DONE | get_platform_fees returns 8 active configs | Rates higher than our original spec (5% vs 3.5%) | PASS
WS-P0-004 | Settlement Automation | Epsilon | DONE | DONE | 646-line service, lifecycle integration, driver pay calc | Functional and production-ready | PASS
WS-P0-005 | Compliance Gate at Assignment | Delta | NOT DONE | NOT DONE | Zero FMCSA/insurance checks in accept() mutation | CRITICAL: Non-compliant carriers can haul hazmat | FAIL
WS-P0-006 | Insurance Gate at Bid Accept | Delta | NOT DONE | NOT DONE | Zero insurance validation in loadBidding.ts | Insurance router exists but is isolated from bid flow | FAIL
WS-P0-007 | Lifecycle WebSocket Events | Zeta | DONE | DONE | emitLoadStatusChange at websocket.ts:426, 17 call sites | Properly integrated across dispatch, loads, AI executor | PASS
WS-P0-008 | Bid WebSocket Events | Zeta | DONE | DONE | emitBidReceived at ws:440, emitBidAwarded at ws:733 | Both fire from esangActionExecutor.ts | PASS
WS-P0-009 | Fleet RBAC | Alpha | DONE | PARTIAL | protectedProcedure on all endpoints, companyId scoping | No requireAccess() calls — granular resource checks missing | NEEDS WORK
WS-P0-010 | Wallet Integrity | Alpha | DONE | DONE | UNIQUE constraint on userId, full audit trail | Schema-level integrity enforced | PASS
WS-P0-011 | Test Accounts (12 Roles) | Delta | NOT DONE | DONE | 12 users with all roles present | ADMIN, DISPATCH, COMPLIANCE_OFFICER, SAFETY_MANAGER added | PASS
WS-P0-012 | Carrier Company + DOT | Delta | NOT DONE | PARTIAL | DOT/MC fields exist and are indexed | Only 1 company, DOT field populated with test data | NEEDS WORK
WS-P0-013 | Test Vehicles | Delta | NOT DONE | DONE | Vehicle schema has 34 types, full tracking | Table operational, seed data present | PASS
WS-P0-014 | Load Date Integrity | Alpha | NOT DONE | NOT DONE | No DB CHECK constraint, no app validation | deliveryDate < pickupDate still possible | FAIL
WS-P0-015 | E2E Smoke Test | All | NOT DONE | NOT DONE | vitest.config.ts exists, zero test files | server/tests/ directory exists but is EMPTY | FAIL
WS-P0-016 | Fee Config Seeding (NEW) | Epsilon | N/A | DONE | 8 fee configs active via get_platform_fees | Seeded as of 2026-03-05 | PASS
WS-P0-017 | Compliance Gate (NEW) | Delta | N/A | NOT DONE | Zero compliance checks in accept() | Same as P0-005 — never implemented | FAIL
WS-P0-018 | Insurance Enforcement (NEW) | Delta | N/A | NOT DONE | Zero insurance checks in bid acceptance | Same as P0-006 — never implemented | FAIL
WS-P0-019 | Immutable Hash-Chain (NEW) | Alpha | N/A | NOT DONE | Zero matches for hashContent/documentHashes/SHA256 | Complete absence — cosmetic signature system unchanged | FAIL
WS-P0-020 | Double-Brokering Prevention (NEW) | Delta | N/A | NOT DONE | Zero matches for originalShipperId/brokerChainDepth | Complete absence — no prevention logic exists | FAIL
FINAL SCORECARD
Total Items Audited | 20
PASS (Fully Done) | 8
NEEDS WORK (Partial) | 4
FAIL (Not Done) | 8
True Completion Rate | 40%
Windsurf Claimed | 100%
Delta (Overclaimed) | 60%

## Technology Expansion Plan
TECHNOLOGY EXPANSION PLAN — VIGA + pplx-embed Integration
How to leverage cutting-edge AI research to make EusoTrip second to none
VIGA — Vision-as-Inverse-Graphics Agent (Paper 1)
Core Innovation: Iterative analysis-by-synthesis loop where a Generator writes code, a Verifier inspects rendered output visually, and corrections feed back through evolving context memory. Achieves 124.70% improvement over one-shot baselines on BlenderBench.
# | Integration Concept | EusoTrip Application | How It Works | Team | Complexity | Impact
1 | VIGA-Powered Load Verification Agent | Automated BOL/POD document verification using iterative visual inspection | Apply VIGA's write→render→compare→revise loop to document verification: 1. Driver uploads photo of BOL/POD 2. Generator extracts expected fields (load #, origin, dest, weight, hazmat class) 3. Verifier compares extracted data against load record in DB 4. If discrepancies found, flags them with visual annotation 5. Iterates until all fields verified or flagged for human review Uses ESANG AI (Gemini 2.5 Flash) as the VLM backbone | Gamma + Alpha | High | Eliminates manual document review; catches forged/incorrect BOLs before freight moves
2 | Visual Load Condition Inspector | AI agent that verifies cargo condition at pickup/delivery by comparing photos | VIGA's multi-view verification applied to cargo inspection: 1. Driver takes photos at PICKUP (baseline condition) 2. Driver takes photos at DELIVERY 3. Verifier agent compares both sets iteratively 4. Uses set_camera-style viewpoint control to examine specific damage areas 5. Generates structured damage report with visual evidence 6. Auto-files accessorial damage claims if needed | Gamma + Zeta | High | Automated damage detection; evidence-based claims; reduced disputes between shippers/carriers
3 | Analysis-by-Synthesis Compliance Dashboard | Self-verifying compliance status that renders expected state and compares against actual | Apply VIGA's Generator/Verifier pattern to compliance monitoring: 1. Generator produces expected compliance state (valid insurance, active authority, clean inspections) 2. System renders actual state from FMCSA + internal data 3. Verifier compares expected vs actual, identifies gaps 4. Memory tracks compliance history across iterations 5. Auto-generates corrective action plans This turns the shareable compliance dashboard (P1-019) into an INTELLIGENT dashboard | Delta + Gamma | Medium | Proactive compliance — catches issues before they cause regulatory violations
4 | Iterative Route Optimization with Visual Feedback | Route planning that renders scenarios and refines based on visual/spatial analysis | VIGA's iterative refinement for route planning: 1. Generator creates initial route plan (OSRM integration already exists) 2. System renders route on map with hazmat restrictions, weigh stations, rest areas 3. Verifier inspects for violations (restricted zones, HOS violations, missing fuel stops) 4. Feeds corrections back → Generator revises route 5. Evolving memory tracks driver preferences and historical patterns Leverages existing OSRM Route Optimizer + Geo Intelligence services | Gamma + Zeta | Medium | Smarter routes that account for hazmat restrictions, driver HOS, and cost optimization
5 | ESANG Cognitive Memory Enhancement | Apply VIGA's evolving context memory to make ESANG's memory system more sophisticated | VIGA uses a sliding-window memory M that retains recent code + verification history. Apply this to ESANG's AgentKeeper CRE (which already has cognitive memory): 1. Structure memory as (action, verification_result) tuples 2. Use TailL sliding window to prevent context bloat 3. Each ESANG action gets verified against actual outcome 4. Failed actions + corrections stored for future reference 5. Memory persists across sessions for each user This makes ESANG self-improving — it learns from its own mistakes | Gamma | Medium | ESANG becomes genuinely intelligent over time; learns user preferences; reduces errors
6 | Skill Library Architecture for Platform Tools | Formalize EusoTrip's tools as a VIGA-style skill library | VIGA separates tools into Generation (make_plan, execute_code) and Verification (investigate, set_camera). Apply same pattern to EusoTrip: Generation tools: create_load, submit_bid, generate_route, create_settlement Verification tools: verify_compliance, inspect_document, check_insurance, validate_rates This creates a formal API that any AI agent can use — not just ESANG. Enables future third-party AI integrations and marketplace | Alpha + Gamma | Low | Extensible AI architecture; third-party AI marketplace potential; clean separation of concerns
pplx-embed — Diffusion-Pretrained Dense Embeddings (Paper 2)
Core Innovation: Multilingual embedding models using diffusion-pretrained bidirectional attention with native INT8 quantization. State-of-the-art retrieval performance across MTEB, MIRACL, ConTEB, and ToolRet. Contextual embeddings retain document-level context in chunk representations.
# | Integration Concept | EusoTrip Application | How It Works | Team | Complexity | Impact
7 | Semantic Load Matching Engine | Replace keyword-based load search with embedding-powered semantic matching | Use pplx-embed to create dense embeddings of: 1. Load descriptions (origin, dest, cargo type, hazmat class, weight, equipment) 2. Carrier profiles (authority, equipment, preferred lanes, safety record) 3. At query time, compute cosine similarity between carrier embedding and available loads 4. INT8 quantization = fast inference at scale (390 docs/MB) 5. Contextual embeddings mean a 'crude oil tanker from Houston' matches 'petroleum transport TX' semantically This supercharges the existing ML Carrier Match model with proper embeddings | Gamma + Alpha | Medium | 10x better load matching; carriers find relevant loads instantly; reduced empty miles
8 | Intelligent Document Search (RAG Enhancement) | Upgrade the existing RAG Retriever with pplx-embed for document/regulation search | EusoTrip already has a RAG Retriever service. Upgrade it: 1. Index all FMCSA regulations, hazmat guides, ERG data using pplx-embed-context-v1 2. Contextual embeddings mean each chunk retains awareness of the full document 3. When a driver asks 'can I transport crude near a school zone?' → retrieve precise regulatory passages 4. INT8 quantization enables indexing the full 9.8M FMCSA records efficiently 5. ToolRet benchmark shows pplx-embed excels at retrieving relevant tools from API docs — perfect for ESANG action selection | Gamma | Medium | ESANG gives precise regulatory answers; compliance officers get instant regulation lookup
9 | Fraud Detection via Embedding Anomalies | Detect suspicious patterns by comparing load/bid embeddings to known fraud signatures | Use pplx-embed's contrastive training to build a fraud detection embedding space: 1. Embed known legitimate load-bid patterns 2. Embed known fraud patterns (double-brokering, identity fraud, rate manipulation) 3. New bids/loads get embedded and compared against both clusters 4. Anomaly = bid embedding closer to fraud cluster than legitimate cluster 5. Binary quantization (1-bit) enables ultra-fast screening of every transaction This enhances the existing Fraud Scorer (Benford/Z-score) with semantic understanding | Gamma + Epsilon | High | Catches sophisticated fraud that rule-based systems miss; real-time screening
10 | Multilingual Carrier Communication | Enable cross-language search and communication for international/multilingual carriers | pplx-embed achieves SOTA on MIRACL (18 languages) and multilingual MTEB. Apply to EusoTrip: 1. Embed all platform content in pplx-embed's multilingual space 2. Spanish-speaking driver searches 'cargas de petroleo en Texas' → matches English load listings 3. Messages between users auto-embedded for semantic search across languages 4. Compliance documents searchable in any of 60+ supported languages 5. Critical for expanding beyond US market | Gamma + Beta | Medium | Opens Latin American, Canadian French, and international markets
11 | Smart Rate Intelligence | Embed historical rate data for intelligent rate prediction and negotiation support | Use pplx-embed's contextual embeddings on rate history: 1. Embed each historical load as: (lane, cargo, season, rate, market_conditions) 2. When shipper posts new load, find semantically similar historical loads 3. Predict fair market rate based on embedding-space neighbors 4. During negotiation, show both parties where the offered rate sits vs. market 5. Contextual training means 'Houston to Cushing crude Jan 2026' retains full context This upgrades the existing Rate Prediction ML model with proper contextual awareness | Gamma + Epsilon | Medium | Data-driven rate negotiation; eliminates pricing guesswork; builds market trust
12 | ESANG Tool Selection via ToolRet | Use pplx-embed's ToolRet capability for ESANG to select the right action from 23+ registered actions | pplx-embed achieves 44.45% nDCG@10 on ToolRet benchmark — designed for tool retrieval. Apply to ESANG: 1. Embed all 23 ACTION_REGISTRY entries with their descriptions 2. When user gives natural language instruction, embed it 3. Retrieve top-k most relevant actions via cosine similarity 4. Eliminates need for exact keyword matching or rigid intent classification 5. Handles ambiguous requests: 'check if that carrier is safe' → [carrier_safety, verify_carrier, carrier_inspections] This makes ESANG truly conversational rather than command-driven | Gamma | Low | ESANG understands intent, not just commands; handles ambiguous requests gracefully

## Windsurf Instructions v3
WINDSURF INSTRUCTIONS v3 — Remaining P0 Fixes + Technology Expansion
Priority | WS-ID | Task | Category | What to Implement (Summary) | Files | Acceptance Criteria | Notes
P0-FIX | WS-P0-005R | Compliance Gate at Assignment | Compliance | Add FMCSA safety rating + operating authority check in loadBidding.ts accept() BEFORE updating load status. Query carrier's company DOT, call FMCSA service, block if Unsatisfactory rating or inactive authority. | frontend/server/routers/loadBidding.ts (lines 318-349) | Bid acceptance throws FORBIDDEN for carriers with: - No DOT number - Unsatisfactory FMCSA rating - Inactive operating authority | THIS WAS NEVER IMPLEMENTED. Windsurf skipped it.
P0-FIX | WS-P0-006R | Insurance Gate at Bid Accept | Compliance | Wire insurance.ts into bid acceptance. Before accepting, query carrier's insurance certs, verify coverage type (hazmat for crude), verify not expired, verify >= $1M coverage. | frontend/server/routers/loadBidding.ts frontend/server/routers/insurance.ts | Bid acceptance rejected when carrier lacks: - Valid auto liability insurance - Cargo insurance - Hazmat endorsement for hazmat loads - Minimum $1M coverage | Insurance router EXISTS (1,391 lines) but is never called from bid flow.
P0-FIX | WS-P0-001R | Add charge.refunded Webhook | Financial | Add case 'charge.refunded' to Stripe webhook handler. On refund: credit wallet back, log reversal, emit financial event. | frontend/server/_core/index.ts (webhook switch, ~line 400) | charge.refunded event properly credits refund to user wallet Refund logged in wallet_transactions emitFinancialEvent fired | Handler exists for 20+ events but refund case is missing.
P0-FIX | WS-P0-002R | Add Payout Idempotency Key | Financial | Add idempotencyKey to stripe.payouts.create() options. Generate key from walletId + amount + timestamp hash. Check for existing key before processing. | frontend/server/routers/wallet.ts (line ~544) | stripe.payouts.create() includes idempotencyKey option Duplicate payout requests return existing payout instead of creating new one | Currently zero idempotency protection.
P0-FIX | WS-P0-014R | Load Date Validation | Data Integrity | Add: 1) DB CHECK constraint: deliveryDate >= pickupDate. 2) App-level validation in load create/update mutations. 3) Fix existing invalid records. | drizzle/schema.ts (loads table) frontend/server/routers/loads.ts | Cannot create load with deliveryDate < pickupDate Existing invalid records corrected DB constraint prevents future violations | No validation exists at any level.
P0-FIX | WS-P0-019R | Immutable Document Hash-Chain | Security | Create documentHashes table. Implement SHA256 content hashing + hash-chain linking. Wire into BOL creation, POD submission, agreement signing. Replace cosmetic signature hash. | drizzle/schema.ts (new table) frontend/server/services/documents/hashChain.ts (new) frontend/server/routers/signatures.ts | Every BOL/POD gets SHA256 content hash Hash-chain links versions verifyChain() returns validity Old cosmetic hash removed | Current signature 'hash' is base64 of first 100 chars — NOT cryptographic.
P0-FIX | WS-P0-020R | Double-Brokering Prevention | Compliance | Add originalShipperId + brokerChainDepth to loads table. Validate in load creation: block broker re-posting of already-brokered loads. Pattern detection for suspicious same-lane reposts. | drizzle/schema.ts frontend/server/routers/loads.ts frontend/server/routers/brokers.ts | BROKER cannot post load already brokered (chain > 1) originalShipperId tracked Suspicious patterns flagged for compliance | Zero implementation exists.
P0-FIX | WS-P0-015R | E2E Smoke Test Suite | QA | Create test files in frontend/server/tests/ using Vitest. Cover: load creation → bid → accept → assign → pickup → delivery → settlement → payout lifecycle. | frontend/server/tests/*.test.ts frontend/vitest.config.ts | At least 1 E2E test covering full load lifecycle All tests pass with vitest run Test files exist and are not empty | vitest.config.ts exists but tests/ dir is empty.
P1-TECH | WS-T1-001 | VIGA Verification Agent for BOL/POD | AI Enhancement | Implement VIGA-inspired iterative document verification: upload photo → extract fields → compare against DB → flag discrepancies → visual annotation. Use ESANG/Gemini as VLM. | frontend/server/services/ai/documentVerifier.ts (new) frontend/server/routers/documents.ts | Driver uploads BOL photo → system extracts load #, origin, dest, weight Extracted data compared against load record Discrepancies flagged with confidence score Human review queue for low-confidence items | Based on VIGA paper: iterative write→render→compare→revise
P1-TECH | WS-T1-002 | pplx-embed Semantic Load Matching | AI Enhancement | Integrate embedding-based semantic search for load matching. Embed loads and carrier profiles, match via cosine similarity. Use INT8 quantization for speed. | frontend/server/services/ai/embeddingService.ts (exists) frontend/server/services/mlEngine.ts | Load search returns semantically relevant results 'crude oil transport Texas' matches 'petroleum hauling Houston' Latency < 100ms for embedding lookup | Based on pplx-embed paper: diffusion-pretrained contextual embeddings
P1-TECH | WS-T1-003 | ESANG Tool Selection via Embeddings | AI Enhancement | Embed all 23 ESANG ACTION_REGISTRY entries. On user query, retrieve top-k actions by embedding similarity instead of keyword matching. | frontend/server/services/esangActionExecutor.ts frontend/server/services/ai/embeddingService.ts | ESANG handles ambiguous requests: 'is that carrier safe?' → [carrier_safety, verify_carrier] Action selection accuracy > 90% on test queries No rigid intent classification needed | Based on pplx-embed ToolRet benchmark (44.45% nDCG@10)
P1-TECH | WS-T1-004 | VIGA Memory System for ESANG | AI Enhancement | Apply VIGA's sliding-window memory to ESANG's AgentKeeper CRE. Store (action, verification_result) tuples. TailL window prevents context bloat. | frontend/server/services/ai/index.ts frontend/server/services/esangActionExecutor.ts | ESANG retains recent action history across sessions Failed actions + corrections stored Memory window = last L interactions Self-improving over time | Based on VIGA Algorithm 1: TailL(Mt ∪ {pt, ct})
P1-TECH | WS-T1-005 | Embedding-Powered Fraud Detection | AI Enhancement | Build fraud detection embedding space. Embed known legitimate and fraudulent patterns. Screen new transactions via embedding distance. | frontend/server/services/ai/fraudScorer.ts (exists) frontend/server/services/ai/embeddingService.ts | New bids screened against fraud embedding cluster Anomaly score returned for each transaction High-risk transactions flagged for review Enhances existing Benford/Z-score system | Based on pplx-embed contrastive training for anomaly detection
P1-TECH | WS-T1-006 | RAG Enhancement with Contextual Embeddings | AI Enhancement | Upgrade existing RAG Retriever with pplx-embed-context-v1 style contextual embeddings. Each chunk retains document-level context. | frontend/server/services/ai/ragRetriever.ts (exists) frontend/server/services/ai/embeddingService.ts | FMCSA regulation queries return precise passages Contextual chunks retain awareness of parent document Driver asks 'hazmat near school?' → retrieves exact CFR section 9.8M FMCSA records indexed efficiently | Based on pplx-embed contextual training (ConTEB SOTA)

## Customer Readiness v2
CUSTOMER READINESS v2 — Post-Windsurf Assessment
Customer | Type | What Works NOW | Still Broken | Blocking P0 Items | Go/No-Go
AMJ Energy | Shipper | Load posting, GPS tracking, AI matching (ESANG), rate negotiation, invoicing, settlement, WS events, document management, 8 fee configs active | No compliance gate (non-compliant carriers can haul), no immutable docs (cosmetic hash only), no refund webhook, no E2E test | P0-005R, P0-019R, P0-001R, P0-015R | NO-GO
Momentum Crude Marketing | Shipper/Broker | All AMJ features + broker tools, rate negotiation with counter-offers, authority management, fee transparency (8 configs) | No double-brokering prevention, no compliance gate, no insurance enforcement, no payout idempotency, no immutable docs | P0-005R, P0-006R, P0-019R, P0-020R, P0-002R | NO-GO
Blue Wing Midstream | Terminal/TAS | SPECTRA-MATCH (crude grade ID), terminal role + dashboard, WS events, AI matching, settlement automation | No shareable compliance dashboard, no immutable docs, appointment system incomplete, no compliance enforcement | P0-005R, P0-019R, P1-019 | NO-GO
MINIMUM VIABLE LAUNCH REQUIREMENTS
To go from NO-GO to GO for all 3 customers, Windsurf must complete these 8 P0-FIX items: 1. WS-P0-005R: Compliance gate at assignment (blocks non-compliant carriers) 2. WS-P0-006R: Insurance enforcement at bid accept (blocks uninsured carriers) 3. WS-P0-001R: charge.refunded webhook (handles Stripe refunds) 4. WS-P0-002R: Payout idempotency key (prevents duplicate payouts) 5. WS-P0-014R: Load date validation (prevents impossible dates) 6. WS-P0-019R: Immutable document hash-chain (real cryptographic verification) 7. WS-P0-020R: Double-brokering prevention (blocks broker→broker chains) 8. WS-P0-015R: E2E smoke test (proves the system works end-to-end) The 6 P1-TECH items (VIGA + pplx-embed integrations) are post-launch differentiators that will make EusoTrip second to none.

## Platform Strengths
WHAT'S WORKING — Platform Strengths (Production-Ready Systems)
System | Evidence | Team Verified | Production Ready?
ESANG AI (Gemini 2.5 Flash) | 1,072-line action executor, 23 registered actions, whitelist architecture, role-based access, Zod validation, audit logging, WebSocket event emission | Gamma | YES
ML Engine (10+ Models) | 1,536-line engine: rate prediction, carrier matching, ETA prediction, demand forecast, anomaly detection, dynamic pricing, churn prediction, load bundling, bid optimizer | Gamma | YES
Real-Time WebSocket (29 Events) | 29 emit functions: load status, bids, GPS, HOS, notifications, messages, gamification, compliance, safety, dispatch, terminal, financial, vehicle, escort, convoy, emergency | Zeta | YES
EusoWallet + Stripe Integration | 2,207-line wallet router, real stripe.payouts.create(), Stripe Connect, 20+ webhook event types, fee calculator (526 lines) | Epsilon | YES (minus idempotency)
Settlement Service | 646-line service: driver pay (5 structures), deductions, bonuses, tax withholding, 1099/W2, HTML statement generation | Epsilon | YES
37-State Load Lifecycle | Complete DRAFT→COMPLETE path with guards, effects, geofence triggers. Covers pickup, transit, delivery, POD, invoicing, payment, settlement | Alpha + Zeta | YES
Rate Negotiation | Multi-round counter-offers, encrypted terms, auto-expiration, thread-based negotiations across loads/lanes/contracts/fuel/accessorials | Epsilon | YES
Authority & Leasing (FMCSR Part 376) | 804-line router: own authority, lease-on/trip lease, lessee/lessor tracking, FMCSA authority lookup | Delta | YES
Gamification System | Points, badges, leaderboard, streaks, mission generation — all wired into ESANG actions | Beta + Gamma | YES
FMCSA Data Integration | 9.8M records across 5 tables, SAFER API integration, carrier safety lookup, inspection history, crash data | Delta | YES (data exists, enforcement missing)
Platform Fee Infrastructure | 8 active fee configs, multi-type calculator (percentage, flat, tiered, hybrid), volume discounts, role-based fees, revenue recording | Epsilon | YES
12 Role Dashboards | DispatchDashboard, SafetyDashboard, ComplianceDashboard, TerminalDashboard, BrokerDashboard, EscortDashboard, DriverDashboard, AdminDashboard, ShipperLoads, SuperAdminDashboard, ZeunAdminDashboard + FleetDashboard | Beta | YES