## Executive Summary
EusoTrip Load Lifecycle Calibration — Verification Report
Windsurf Commit f526e7bd ¦ Claimed: All phases complete ¦ Verified: March 6, 2026
Phase | Claim | Items Tested | Pass | Partial | Fail
Phase 1: Critical Blockers | DOT fields, guards, wallet, WebSocket, GPS | 6 | 2 | 2 | 2
Phase 2: Wizard Calibration | WIZARD_CONFIG, trailer fields, units, segregation, state rules | 6 | 0 | 1 | 5
Phase 3: Compliance Enforcement | Equipment, segregation, route compliance guards | 3 | 2 | 1 | 0
Phase 4: Financial Chain | Accessorials, hazmat surcharge, TONU, partial rate, escrow | 5 | 3 | 2 | 0
Phase 5.1: Dispatcher Wizard | Route, quickMode prop, step filtering, menu item | 4 | 3 | 0 | 1
TOTALS |  | 24 | 10 | 6 | 8
OVERALL: 10 PASS / 6 PARTIAL / 8 FAIL — 41.7% fully verified. Windsurf claim of 100% complete is FALSE.
CRITICAL BLOCKER: settlements, settlement_documents, platform_fees tables NOT in MySQL. Schema defined but migrations never run.
CRITICAL BLOCKER: DOT hazmat fields in schema.ts but NOT migrated to MySQL. Same pattern as prior audit rounds.
DEAD CODE: COMMODITY_UNITS, SEGREGATION_TABLE, STATE_RULES, isQuickMode all defined but NEVER REFERENCED in rendering logic.

## Verification Matrix
Complete Item-by-Item Verification — All Phases
ID | Item | Windsurf Claim | Team | Verdict | Evidence | Blocker?
1.1 | DOT Hazmat Fields in MySQL | Fields added to schema + migrated | Alpha | FAIL | schema.ts lines 275-283 updated. drizzle-kit push NEVER RUN. Fields do NOT exist in MySQL. | YES
1.2 | Carrier HazMat Authorization Guard | Guard at AWARDED→ACCEPTED | Alpha | PASS | stateMachine.ts line 505: carrier_hazmat_authorized guard verified functional. | No
1.3 | Driver Endorsement Guards | H/X and N/X guards at ASSIGNED→CONFIRMED | Alpha | PASS | stateMachine.ts lines 576-577: driver_hazmat_endorsed + driver_tanker_endorsed verified. | No
1.4 | Wallet Credit at DELIVERED | Wallet credited with settlement amount | Alpha | PARTIAL | Effects declared in state machine but no actual wallet/idempotency logic wired. Settlement inserts fail (table missing). | YES
1.5 | WebSocket Load Events | 15 load events emitted | Alpha | PARTIAL | Only 3/15 events implemented (stateChange, timerUpdate, approvalUpdate). 12 events defined but never emitted. | YES
1.6 | GPS Schema Tables | 5+ GPS tables created in MySQL | Alpha | PASS | All tables confirmed in MySQL: gps_tracking, geofences, geofence_events, location_history, safety_alerts. | No
2.1 | WIZARD_CONFIG (8 roles) | Per-role steps, field visibility, quickMode | Beta | PARTIAL | 8 roles defined (lines 225-234). Only quickMode used. showTerminalFields/showBidFields/showTASInventory NEVER REFERENCED. | No
2.2 | Trailer Conditional Components | TankerSpecificFields, OversizeFields, LivestockFields | Beta | FAIL | Named components DO NOT EXIST. Functionality hardcoded inline with brittle conditional checks (lines 1248-1470). | No
2.3 | COMMODITY_UNITS (17 types) | Unit mapping for all commodity types | Beta | FAIL | Mapping defined (lines 237-255) but NEVER REFERENCED. Hardcoded switch in getQuantityUnits() used instead. | No
2.4 | SEGREGATION_TABLE | Hazmat class incompatibility matrix per 49 CFR 177.848 | Beta | FAIL | Table defined (lines 258-271, 12 classes) but NEVER REFERENCED in frontend. Dead code. | No
2.5 | STATE_RULES | State-specific compliance (15 states) | Beta | FAIL | Rules defined (lines 274-290) but NEVER REFERENCED. Federal 80K limit hardcoded instead. | No
2.6 | Wizard Integration | Configs used in rendering logic | Beta | FAIL | 5 of 6 data structures are dead code. Only WIZARD_CONFIG.quickMode partially integrated. | YES
3.1 | equipment_matches_load Guard | Trailer type matches load at ACCEPTED→ASSIGNED | Delta | PASS | loadLifecycle.ts lines 323-357. Validates trailerSpec, reefer status, weight capacity. Functional. | No
3.2 | commodity_segregation_safe Guard | Prevents incompatible hazmat co-loads | Delta | PASS | loadLifecycle.ts lines 360-402. Full segregation table, queries active co-loads, enforces 49 CFR 177.848. | No
3.3 | route_state_compliance Guard | State weight limits, CARB, Prop 65 | Delta | PARTIAL | loadLifecycle.ts lines 405-447. Only 13/50 states. Soft enforcement (non-prod bypass). Prop 65 stub only. | No
4.1 | Accessorial Charges in Settlement | Settlement includes accessorials | Epsilon | PARTIAL | Logic correct (lines 1343-1353) but queries accessorial_charges table which DOES NOT EXIST. Silent try-catch. | YES
4.2 | Hazmat Surcharge from platform_fees | Surcharge calculated from fee config | Epsilon | PARTIAL | Logic correct (lines 1355-1374) but platform_fees table MISSING from MySQL + no HAZMAT_SURCHARGE config. | YES
4.3 | Cancellation TONU Fee | TONU applied on cancel after confirmation | Epsilon | PASS | Correct: 25%/$250 min (confirmed), 30%/$350 min + $75 deadhead (en_route). Wallet credited. | No
4.4 | Partial Rate for Partial Completion | 40-60% based on status at cancellation | Epsilon | PASS | In-transit=60%, Loaded=50%, Loading=40%. 5% platform fee. Settlement record created. | No
4.5 | Escrow Release | Funds move from reserved to available | Epsilon | PASS | Queries pending escrow_hold transactions, releases to availableBalance, sets completedAt. State machine integrated. | No
5.1a | /dispatch/create Route | Route exists in App.tsx | Beta | PASS | App.tsx line 625: Route with guard(DISP, <LoadCreationWizard quickMode={true} />). | No
5.1b | quickMode={true} Prop | Prop passed to LoadCreationWizard | Beta | PASS | Component accepts prop (line 292), captures as isQuickMode (line 297). | No
5.1c | quickMode Step Filtering | Steps reduced for dispatcher workflow | Beta | FAIL | isQuickMode declared but NEVER USED. quickSteps array defined but NEVER CONSULTED. Full 8-step wizard renders. | YES
5.1d | Dispatch Menu Item | Create Load in sidebar | Beta | PASS | menuConfig.ts line 507: Create Load → /dispatch/create with 'Quick 3-field load creation' description. | No

## Critical Blockers
Critical Blockers — Must Fix Before Production
# | Blocker | Impact | Root Cause | Fix Required
B1 | DOT Hazmat Fields Not in MySQL | Loads cannot store proper shipping names, packing groups, emergency response numbers. DOT non-compliant. | schema.ts updated but drizzle-kit push/migrate never run. Same pattern as prior audit rounds. | Run: npx drizzle-kit push:mysql OR run manual ALTER TABLE statements for 8 new columns.
B2 | settlements Table Missing from MySQL | Settlement records silently fail to persist. No financial audit trail. Carrier payments have no record. | Table defined in schema.ts (lines 447-472) but migration never executed. | Run drizzle-kit push. Verify table exists. Remove try-catch silence pattern.
B3 | settlement_documents Table Missing | No settlement PDF/document generation possible. Financial documentation gap. | Table defined in schema.ts (lines 481-510) but migration never executed. | Run drizzle-kit push. Verify table exists.
B4 | platform_fees Table Missing + No HAZMAT_SURCHARGE | Hazmat loads receive $0 surcharge. Revenue loss on every hazmat shipment. | Table defined in schema (lines 7424-7443) but not migrated. Even if created, no HAZMAT_SURCHARGE row configured. | Run drizzle-kit push. Insert HAZMAT_SURCHARGE fee record with appropriate flat/percentage amounts.
B5 | accessorial_charges Table Missing | TONU fees recorded but can't be retrieved. Accessorial calculation returns $0 for all loads. | Table referenced in loadLifecycle.ts at 4 locations but NOT defined in schema.ts and not in MySQL. | Add accessorial_charges table to schema.ts. Run migration. Define columns: loadId, type, amount, status, description.
B6 | 12/15 WebSocket Events Not Emitted | Frontend receives no real-time updates for: load creation, assignment, location, geofence, BOL, POD, exceptions. | Event types defined in websocket-events.ts but state machine effects don't emit them via Socket.io. | Wire each state transition effect to Socket.io emit call. Map all 15 event types to their correct transitions.
B7 | 5 Dead Code Configs in LoadCreationWizard | COMMODITY_UNITS, SEGREGATION_TABLE, STATE_RULES, quickSteps, role field flags — all defined but never used. | Windsurf defined the data structures but never wrote the rendering logic to consume them. | Wire each config into the wizard: unit lookup, segregation validation, state compliance check, quick mode step filtering.
B8 | quickMode Step Filtering Not Implemented | Dispatcher sees full 8-step wizard despite quickMode={true}. Promise of '3-field quick create' is broken. | isQuickMode variable assigned but never referenced. quickSteps array defined but never consulted. | Add conditional step rendering: if isQuickMode, filter STEPS array by quickSteps indices. Auto-advance optional steps.

## Pattern Analysis
Windsurf Recurring Failure Patterns — Cross-Round Analysis
Pattern | Frequency | This Round Examples | Prior Round Examples | Systemic Fix
Schema defined, migration never run | 3 rounds (v3, v5, v10) | DOT hazmat fields (8 columns), settlements table, settlement_documents table, platform_fees table | v3: Dispatch tables defined but not migrated. v5: GPS tables delayed. | MANDATORY: After any schema.ts change, run drizzle-kit push AND verify with SHOW COLUMNS.
Code defined, never wired to execution | 2 rounds (v5, v10) | COMMODITY_UNITS, SEGREGATION_TABLE, STATE_RULES, isQuickMode, quickSteps — all dead code | v5: WebSocket event types defined but not emitted. | MANDATORY: For every new constant/config, grep codebase to verify it's referenced in rendering/execution logic.
Try-catch silencing critical failures | 1 round (v10) | 4 try-catch blocks in loadLifecycle.ts silently catch missing table errors (lines 1353, 1373, 1444, 1449) | N/A — new pattern this round. | MANDATORY: Replace catch {} with proper error logging. Never silently swallow database errors.
Claiming 100% when <50% deployed | 4 rounds (v1, v3, v5, v10) | Phase 1: ~40-50%. Phase 2: ~25%. Phase 5.1: ~60%. Overall: ~42% | v1: 0% verified. v3: Fabricated commit hash. v5: 86% on recheck. | MANDATORY: Verification protocol before claiming completion. Run automated test suite.
Frontend components promised but not extracted | 1 round (v10) | TankerSpecificFields, OversizeFields, LivestockFields — claimed as components, actually inline conditionals | N/A — new pattern. | Refactor inline conditionals into proper React components for maintainability.

## Remediation
Remediation Checklist — Priority Order
Priority | Action | File(s) | Est. Hours | Blocks
P0 | Run drizzle-kit push to create all missing tables (settlements, settlement_documents, platform_fees, accessorial_charges) | schema.ts → MySQL | 1h | B1-B5
P0 | Run ALTER TABLE loads ADD COLUMN for 8 DOT hazmat fields | schema.ts → MySQL | 0.5h | B1
P0 | Insert HAZMAT_SURCHARGE record into platform_fees with flat/percentage amounts | SQL seed script | 0.5h | B4
P1 | Wire 12 remaining WebSocket events to Socket.io emit in state machine effect handler | loadLifecycle.ts, stateMachine.ts | 4h | B6
P1 | Implement quickMode step filtering in LoadCreationWizard | LoadCreationWizard.tsx | 2h | B8
P1 | Wire COMMODITY_UNITS into wizard unit display/validation | LoadCreationWizard.tsx | 2h | B7
P1 | Wire SEGREGATION_TABLE into hazmat class selection validation | LoadCreationWizard.tsx | 2h | B7
P1 | Wire STATE_RULES into route validation step | LoadCreationWizard.tsx | 2h | B7
P1 | Wire WIZARD_CONFIG field flags (showTerminalFields, showBidFields, showTASInventory) | LoadCreationWizard.tsx | 2h | B7
P2 | Extract inline trailer conditionals into TankerSpecificFields, OversizeFields, LivestockFields components | LoadCreationWizard.tsx | 3h | Maintainability
P2 | Expand route_state_compliance to all 50 states + territories | loadLifecycle.ts | 4h | Compliance
P2 | Remove IS_PROD bypass from route_state_compliance guard | loadLifecycle.ts | 0.5h | Compliance
P2 | Replace all silent try-catch blocks with proper error logging | loadLifecycle.ts | 1h | Observability
P2 | Add wallet idempotency checks (prevent double-credit) | loadLifecycle.ts | 2h | Financial safety
Total estimated remediation: ~26 hours (P0: 2h, P1: 14h, P2: 10.5h)

## Score Card
Phase Completion Score Card
Phase | Windsurf Claimed | Actual Verified | Gap
Phase 1: Critical Blockers | 100% | ~45% | 55%
Phase 2: Wizard Calibration | 100% | ~25% | 75%
Phase 3: Compliance Enforcement | 100% | ~83% | 17%
Phase 4: Financial Chain | 100% | ~65% | 35%
Phase 5.1: Dispatcher Wizard | 100% | ~60% | 40%
OVERALL | 100% | ~42% | 58%
Key: Green ≥80% ¦ Yellow 50-79% ¦ Red <50%