## Executive Summary
EusoTrip Load Lifecycle — Re-Fix Verification (Commit f011fe98)
Previous round: 10 PASS / 6 PARTIAL / 8 FAIL (42%) ¦ This round verified March 6, 2026
Phase | Items Tested | Pass | Partial | Fail | Previous | Delta
Phase 1: DB Schema & Tables | 8 | 6 | 1 | 1 | ~45% | +30%
Phase 2: Wizard Calibration | 6 | 6 | 0 | 0 | ~25% | +75%
Phase 3: Compliance (50 states) | 2 | 2 | 0 | 0 | ~83% | +17%
Phase 5.1: Dispatcher Quick-Create | 2 | 2 | 0 | 0 | ~60% | +40%
WebSocket Emissions | 5 | 4 | 0 | 1 | 3/15 | +4 blocks
TOTALS | 23 | 20 | 1 | 2
OVERALL: 20 PASS / 1 PARTIAL / 2 FAIL — 87% verified. Major improvement from 42%.
REMAINING: 2 items still need fixing (see Critical Blockers sheet)

## Verification Matrix
Complete Item-by-Item Verification — Re-Fix Round
ID | Item | Windsurf Claim | Team | Verdict | Evidence | Previous
1.1 | DOT Hazmat Columns in MySQL | 8 columns via addColIfMissing() | Alpha | PASS | All 8 columns verified in MySQL: properShippingName, packingGroup, technicalName, emergencyResponseNumber, emergencyPhone, hazardClassNumber, subsidiaryHazards, specialPermit | FAIL
1.2 | settlements Table | Created via ensureTable() | Alpha | PASS | Table exists with 17 columns. Correct schema: loadId, shipperId, carrierId, loadRate, platformFeeAmount, carrierPayment, accessorialTotal, hazmatSurcharge, status. | FAIL
1.3 | settlement_documents Table | Created via ensureTable() | Alpha | PASS | Table exists with 13 columns. Correct schema: loadId, documentType, amount, deductions (JSON), netPay, status, finalizedAt. | FAIL
1.4 | platform_fees Table | Created via ensureTable() | Alpha | PASS | Table exists with 15 columns. feeType enum includes HAZMAT_SURCHARGE. effectiveFrom/To temporal fields present. | FAIL
1.5 | accessorial_charges Table | Created via ensureTable() | Alpha | PASS | Table exists with 10 columns: loadId, type, amount, status (pending/approved/auto_approved/rejected/paid), approvedBy. | FAIL
1.6 | HAZMAT_SURCHARGE Seed Data | Not explicitly claimed | Alpha | FAIL | platform_fees table is EMPTY. No HAZMAT_SURCHARGE row exists. Query returned 0 rows. Feature non-functional without config. | FAIL
1.7 | Silent Try-Catch Removal | Not explicitly claimed | Alpha | PARTIAL | addColIfMissing() still swallows 'Duplicate column' errors silently. ensureTable() logs warnings. Justified for schema ops but not fully clean. | PARTIAL
1.8 | Implementation Quality | addColIfMissing + ensureTable | Alpha | PASS | Parameterized queries, information_schema checks, proper logging, type-safe TypeScript. Professional quality. | N/A
2.1 | activeStepIndices useMemo | Dynamically filters steps by role | Beta | PASS | Lines 626-631: useMemo with [isHazmat, isQuickMode, wizConfig.quickSteps] deps. Maps to ALL_STEPS correctly. | FAIL
2.2 | DISPATCH 5-Step Wizard | Indices [0,1,4,6,7] | Beta | PASS | WIZARD_CONFIG line 228: quickMode:true, quickSteps:[0,1,4,6,7]. Renders: Trailer, Product, Origin/Dest, Pricing, Review. | FAIL
2.3 | COMMODITY_UNITS Auto-Setting | Via TRAILER_COMMODITY_MAP | Beta | PASS | Line 1028: On trailer select, looks up TRAILER_COMMODITY_MAP[id] → COMMODITY_UNITS[type] → sets volumeUnit + weightUnit. | FAIL
2.4 | SEGREGATION_TABLE Warning Panel | Red panel with 49 CFR 177.848 | Beta | PASS | Lines 1099-1104: Live red panel (bg-red-500/10) shows incompatible classes when hazmatClass selected. References 49 CFR 177.848. | FAIL
2.5 | STATE_RULES 50-State Banners | Amber compliance banners | Beta | PASS | Lines 274-325: All 50 states. Lines 2084-2105: Amber panel (bg-amber-500/10) shows weight limits, CARB req, hazmat notes. | FAIL
2.6 | showTerminalFields Gating | Gates terminal picker by role | Beta | PASS | Lines 1966-2002: Renders terminal picker only for TERMINAL_MANAGER/ADMIN/SUPER_ADMIN + requires myTerminals.length > 0. | FAIL
3.1 | route_state_compliance 50 States | Expanded from 13 to 50 | Delta | PASS | Lines 416-467: All 50 states with weight limits. MI=164K, MT=131K. CA has CARB. 11 states have hazmat notes. | PARTIAL
3.2 | IS_PROD Bypass Removed | Enforce in all environments | Delta | PASS | Lines 479-483: Comment says 'Enforce in all environments — no bypass'. No IS_PROD conditional in block. | N/A
5.1a | quickMode Step Filtering | DISPATCH sees filtered steps | Beta | PASS | Line 629: if (isQuickMode && wizConfig.quickSteps) indices = indices.filter(). Functional, tested. | FAIL
5.1b | Menu + Route | /dispatch/create → LoadCreationWizard | Beta | PASS | App.tsx line 625 + menuConfig.ts line 507. Both confirmed from prior round (unchanged). | PASS
WS-1 | emitFinancialEvent | DELIVERED/CANCELLED/DISPUTE | Zeta | PASS | websocket.ts lines 638-647: broadcastToChannel(USER). Called at lines 1627+1638 for shipper+catalyst. | PARTIAL
WS-2 | emitDispatchEvent | 8 dispatch states | Zeta | PASS | websocket.ts lines 613-633: broadcastToChannel(DISPATCH). Called at line 1658. Urgent priority broadcasts separately. | PARTIAL
WS-3 | emitComplianceAlert | WEIGHT_VIOLATION | Zeta | PASS | websocket.ts lines 553-571: Dual broadcast to COMPANY + COMPLIANCE_ALERTS channels. Called at line 1677. | PARTIAL
WS-4 | emitGamificationEvent | XP on delivery | Zeta | PASS | websocket.ts lines 535-548: broadcastToChannel(USER). Called at lines 1697+1705 for driver (100XP) + catalyst (50XP). | PARTIAL
WS-5 | Original 15 LOAD_EVENTS | Not explicitly claimed | Zeta | FAIL | 0 of 15 original load:* events from websocket-events.ts are emitted. New blocks use custom event types, NOT standardized LOAD_EVENTS constants. | PARTIAL

## Remaining Blockers
Remaining Blockers — 2 Items
# | Blocker | Impact | Root Cause | Fix Required
B1 | HAZMAT_SURCHARGE Not Seeded in platform_fees | Hazmat loads receive $0 surcharge. Revenue loss on every hazmat shipment. The calculation logic works but returns $0 because no fee config exists. | platform_fees table was created (PASS) but no seed data inserted. Table is completely empty. | INSERT INTO platform_fees (feeType, name, description, percentage, flatAmount, active, effectiveFrom, createdAt, updatedAt) VALUES ('HAZMAT_SURCHARGE', 'Hazmat Load Surcharge', 'Additional charge for hazardous materials transport', '2.500', '50.00', true, NOW(), NOW(), NOW());
B2 | Original 15 LOAD_EVENTS Not Emitted | Frontend clients subscribing to load:created, load:posted, load:assigned, load:location_updated, load:geofence_enter/exit, load:document_uploaded, load:bol_signed, load:pod_submitted receive NO events. The 4 new emit blocks use custom event types instead. | Windsurf created 4 new emission functions with custom event types rather than wiring the 15 existing LOAD_EVENTS constants from websocket-events.ts. | In loadLifecycle.ts state machine effects, emit the standardized events: import { LOAD_EVENTS } from 'shared/websocket-events' and emit LOAD_EVENTS.LOAD_CREATED at DRAFT→POSTED, LOAD_EVENTS.LOAD_ASSIGNED at AWARDED→ACCEPTED, etc. Map all 15 events to their correct state transitions.

## Progress Tracker
Verification Progress — Round-over-Round
Phase | v10 Initial Claim | v10 Round 1 Verified | v10 Round 2 Verified | Status
Phase 1: Critical Blockers | 100% | 45% | 88% | Near Complete
Phase 2: Wizard Calibration | 100% | 25% | 100% | DONE
Phase 3: Compliance | 100% | 83% | 100% | DONE
Phase 4: Financial Chain | 100% | 65% | 75% | Seed data needed
Phase 5.1: Dispatcher Wizard | 100% | 60% | 100% | DONE
WebSocket Events | 100% | 20% | 60% | 15 std events missing
OVERALL | 100% | 42% | 87% | 2 blockers remain