## Executive Summary
EUSOTRIP PRODUCTION READINESS — MASTER AUDIT REPORT
Generated: March 04, 2026 ¦ 6-Team Multi-Agent Audit ¦ All 12 User Types
TEAM VERDICTS
Team | Domain | Overall Verdict | Key Strength | Critical Gap | Production Readiness
TEAM ALPHA | Backend & Data | PRODUCTION-READY with gaps | 169 routers, 205 tables, 540+ procedures, 37-state lifecycle | RBAC missing on fleet.ts; 2 orphaned wallets; no unique constraint on bids | 85%
TEAM BETA | Frontend & UX | FEATURE-COMPLETE, needs organization | 369 pages, enterprise-grade dashboards, consistent design system | 8 of 12 role directories empty (pages scattered in root); missing error/empty states | 75%
TEAM GAMMA | AI & Intelligence | PRODUCTION-GRADE — NOT STUBS | Real Gemini 2.5 Flash, 10 ML models, cognitive memory, 30+ executable actions | Depends on GEMINI_API_KEY; no secondary LLM fallback; limited historical data | 90%
TEAM DELTA | Compliance & Regulatory | EXCELLENT DATA, POOR ENFORCEMENT | 9.8M FMCSA records, 50+ doc types, insurance monitoring, daily compliance scans | NO compliance gates at load assignment; insurance minimums not enforced; safety scores not blocking | 60%
TEAM EPSILON | Financial & Transactions | STRUCTURE-READY, FLOWS BROKEN | 2,207-line wallet, real Stripe integration, 26 accessorial types, fee calculator | Money flows IN but never OUT; no payout execution; no webhooks; $0 fees configured; no settlements | 40%
TEAM ZETA | Real-Time & Comms | ARCHITECTURE SOUND, EVENTS MISSING | Native WS 140+ events, GPS 30-sec, geofencing, multi-channel notifications | Load lifecycle transitions don't emit WS events; bids don't emit events; no Lobby | 70%
OVERALL PLATFORM READINESS
VERDICT: NOT YET PRODUCTION-READY — 15 P0 fixes required before customer onboarding
CRITICAL NUMBERS
Metric | Count | Status
P0 Critical Issues | 15 | MUST FIX before launch
P1 High Issues | 18 | Fix within Sprint 1
P2 Medium Issues | 12 | Fix within Sprint 2
P3 Low Issues | 8 | Backlog
Total Findings | 53 | Across all 6 teams
Windsurf Instructions Generated | 35 | Prioritized and consensus-reviewed
Estimated Fix Time (P0+P1) | 2-3 weeks | With dedicated Windsurf effort

## Windsurf P0 Instructions
P0 CRITICAL — WINDSURF INSTRUCTIONS (DO FIRST)
These 15 items MUST be fixed before any customer onboarding. Each has cross-team consensus.
ID | Team(s) | Category | Title | Issue Description | Required Change (Precise) | Files to Modify | Verification | Consensus
WS-P0-001 | Epsilon | Financial | Implement Stripe webhook receiver | No webhook endpoint exists. Payment events (succeeded, refunded, transfer) never captured. Money enters Stripe but platform has no record of completion. | Create /api/webhooks/stripe endpoint. Handle: payment_intent.succeeded (credit wallet, create settlement), charge.refunded (debit wallet), transfer.created (update payout status), payout.paid (mark complete). Use stripe.webhooks.constructEvent() for signature verification. | frontend/server/routers/stripe.ts OR new frontend/server/webhooks/stripe.ts | POST to webhook endpoint with test event → DB records created; Stripe dashboard shows webhook delivery success | Epsilon + Alpha + Zeta
WS-P0-002 | Epsilon | Financial | Implement payout execution in wallet.requestPayout() | requestPayout() creates DB record but NEVER calls stripe.transfers.create() or stripe.payouts.create(). Drivers cannot withdraw money. | In wallet.ts requestPayout mutation: after DB insert, call stripe.transfers.create({ amount, currency:'usd', destination: user.stripeConnectId }). Update wallet_transactions status on success/failure. Add idempotency key. | frontend/server/routers/wallet.ts (requestPayout procedure, ~line 500+) | Call requestPayout → Stripe transfer created → wallet balance decremented → wallet_transactions shows 'completed' status | Epsilon + Alpha
WS-P0-003 | Epsilon | Financial | Seed platform fee configurations | get_platform_fees() returns empty array []. Fee calculator defaults to $0. Platform earns zero revenue on all transactions. | Insert into platform_fee_configs (or equivalent table): load_booking 5% base, instant_pay 2%, cash_advance 3.5%, p2p_transfer 1%, accessorial 3.5%. Set createdBy = super admin userId. Mark isActive = true. | Database seed script OR frontend/server/routers/platformFees.ts | get_platform_fees() returns 5+ active fee configs; feeCalculator.calculateFee() returns non-zero for load payments | Epsilon + Alpha
WS-P0-004 | Epsilon | Financial | Create settlement automation job | No settlement runner exists. Driver earnings accumulate but no weekly/monthly settlement closes the cycle. No settlements table confirmed. | Create settlement cron job (weekly): 1) Query all loads with status=delivered that lack settlements, 2) Calculate amounts (load rate - platform fee - accessorials), 3) Create settlement record, 4) Credit carrier wallet, 5) Update load status to PAID. Verify settlements table exists (create migration if not). | New: frontend/server/cron/settlements.ts + database migration if needed | run_sql_query SELECT from settlements returns records; wallet balances update after settlement runs | Epsilon + Alpha + Delta
WS-P0-005 | Delta | Compliance | Implement compliance gate at load assignment | Loads can be assigned to drivers/carriers without checking: insurance active, FMCSA safety status, driver endorsements, document validity. Violation of DOT regulations. | In dispatch.ts assignLoad() and loadLifecycle transitionState() for ASSIGNED state: 1) Call evaluateCompanyCompliance(companyId) → block if non-compliant, 2) Call getInsuranceStatus(dotNumber) → block if expired/insufficient, 3) Check driver hazmat/tanker endorsement expiry dates → block if expired, 4) Query FMCSA SMS scores → block if Unsatisfactory rating or active OOS. Return specific error message for each gate failure. | frontend/server/routers/dispatch.ts (assignLoad), frontend/server/routers/loadLifecycle.ts (ASSIGNED transition guard) | Attempt to assign load with expired insurance → error 'Insurance expired'; assign with OOS carrier → error 'Carrier out of service' | Delta + Alpha + Epsilon
WS-P0-006 | Delta | Compliance | Add insurance minimum verification at bid acceptance | loadBidding.ts accept() proceeds without confirming carrier has required insurance. For crude oil/hazmat loads, 49 CFR 387.9 requires $5M coverage. | In loadBidding accept() mutation: 1) Look up load's hazmat class, 2) Check HAZMAT_CLASS_REQUIREMENTS mapping for required insurance minimum, 3) Query carrier's insurance policies + FMCSA insurance on file, 4) Block if coverage < required minimum. Include insurance minimum in bid rejection message. | frontend/server/routers/loadBidding.ts (accept procedure) | Submit bid from carrier with $1M insurance on $5M-required hazmat load → bid acceptance blocked with 'Insufficient insurance coverage' error | Delta + Epsilon + Alpha
WS-P0-007 | Zeta | Real-Time | Add WebSocket event emission to load lifecycle transitions | loadLifecycle.ts state transitions update DB but NEVER call emitLoadStatusChange(). Dispatch/shipper clients must poll for updates instead of receiving real-time push. | In loadLifecycle.ts transitionState() mutation: after successful DB state update, call emitLoadStatusChange({ loadId, fromState, toState, userId, timestamp }). Emit to channels: load:{loadId}, dispatch:{companyId}, fleet:{companyId}. Also emit on geofence-triggered transitions. | frontend/server/routers/loadLifecycle.ts (transitionState effect handlers, ~lines 500-1000) | Transition load state → WebSocket client receives load:status:changed event within 1 second | Zeta + Alpha
WS-P0-008 | Zeta | Real-Time | Add WebSocket event emission to bid submission | loadBidding.ts submit() creates bid in DB but NEVER calls emitBidReceived(). Shippers don't get real-time bid notifications. | In loadBidding.ts submit() mutation: after successful bid insert, call emitBidReceived({ loadId, bidId, bidAmount, bidderName, bidderRole }). Emit to channels: load_bids:{loadId}, load:{loadId}. Also emit on counter-offer submission. | frontend/server/routers/loadBidding.ts (submit procedure, ~line 244) | Submit bid → shipper's WebSocket client receives bid:received event within 1 second | Zeta + Alpha
WS-P0-009 | Alpha | Security | Add RBAC guards to fleet.ts router | fleet.ts has NO requireAccess() calls. Any authenticated user can view/modify any company's vehicles, geofences, and fleet data. Multi-tenant isolation broken. | Add requireAccess({ userId, role, action: 'READ'/'UPDATE'/'DELETE', resource: 'fleet', targetOwnerId/targetCompanyId }) to ALL fleet.ts procedures: getGeofences, getGeofenceStats, deleteGeofence, getVehicles, createVehicle, updateVehicle. Use ownershipFilter() on all SELECT queries. | frontend/server/routers/fleet.ts (all procedures, lines 21-100+) | User from Company A queries fleet → only sees Company A vehicles; attempt to access Company B fleet → 403 FORBIDDEN | Alpha + Delta
WS-P0-010 | Alpha | Data | Fix orphaned wallet records | Wallets with userId=0 and userId=2 reference non-existent users. Payment processing will fail for these wallets. | DELETE FROM wallets WHERE userId IN (0, 2). These are test artifacts. Alternatively, if users were deleted, ensure cascade deletes clean up wallets in future. | Database: wallets table (rows with userId=0 and userId=2) | run_sql_query 'SELECT COUNT(*) FROM wallets WHERE userId NOT IN (SELECT id FROM users)' returns 0 | Alpha + Epsilon
WS-P0-011 | Alpha | Data | Create test accounts for all 12 user types | 5 of 12 user types have no test accounts: CARRIER, ADMIN, COMPLIANCE_OFFICER, SAFETY_MANAGER, FACTORING. Cannot test their workflows. | Create users: carrier@eusotrip.com (role=CARRIER, companyId=test carrier company), admin@eusotrip.com (ADMIN), compliance@eusotrip.com (COMPLIANCE_OFFICER, companyId=test), safety@eusotrip.com (SAFETY_MANAGER, companyId=test), factoring@eusotrip.com (FACTORING). Auto-create wallets via ensureWallet(). Set isVerified=true, isActive=true. | Database seed script or registration flow | list_users shows all 12 roles present; get_user_details for each returns valid profile with wallet | Alpha + Beta + All Teams
WS-P0-012 | Alpha | Data | Register test carrier company with DOT/MC | Only 1 company (Eusorone) with empty DOT/MC and 'pending' compliance. No carrier company exists to test carrier workflows. | Insert company: name='Test Carrier LLC', dotNumber='2233825' (or valid TX carrier DOT), mcNumber='MC-123456', complianceStatus='verified', state='TX'. Assign carrier, driver, catalyst, escort test users to this company via companyId. | Database: companies table + users.companyId updates | search_companies shows 2+ companies; FMCSA lookup with DOT returns data; carrier users have companyId set | Alpha + Delta
WS-P0-013 | Alpha | Data | Register test vehicles for carrier fleet | vehicles table has 0 rows. Carriers cannot assign equipment to loads. Driver assignment requires vehicle. | Insert 3 vehicles: 1) Peterbilt 389 tanker truck (VIN, plate, status=active, companyId=carrier company), 2) MC-407 tanker trailer (capacity=9000gal), 3) Dry van trailer. Set all as active with valid inspection dates. | Database: vehicles table | Fleet page shows 3 vehicles; load assignment dropdown includes available vehicles | Alpha + Delta + Beta
WS-P0-014 | Alpha | Data | Fix load data integrity issues | Load 11 has deliveryDate (Feb 2) BEFORE pickupDate (Mar 2). 6 loads have lat/lng 0,0. 5 loads missing distance. Inconsistent load number format. | 1) Update load 11: deliveryDate = 2026-03-03, 2) Geocode addresses for loads 1-6 to get real lat/lng, 3) Calculate distances for loads 1-5 using haversine, 4) Add validation in loads.create: deliveryDate must be >= pickupDate. | Database: loads table + frontend/server/routers/loads.ts (create validation) | All loads have non-zero lat/lng; all loads have distance; load 11 deliveryDate > pickupDate | Alpha
WS-P0-015 | All Teams | End-to-End | Execute complete load lifecycle test | ZERO loads have progressed past 'posted'. Zero bids exist. The entire platform workflow is untested end-to-end. | After WS-P0-001 through WS-P0-014 are complete: 1) Shipper creates load (with ESANG AI), 2) Carrier (catalyst) submits bid (with bid fairness analysis), 3) Shipper accepts bid → load AWARDED, 4) Catalyst assigns driver+vehicle → ASSIGNED, 5) Driver picks up → IN_TRANSIT (GPS starts), 6) Driver delivers → DELIVERED (POD captured), 7) Settlement created → PAID (wallet credited). Verify ALL WebSocket events fire. Verify compliance gates block non-compliant test. | All load, bidding, lifecycle, wallet, settlement, tracking files | search_loads shows loads in multiple statuses; load_bids has entries; wallet_transactions has entries; GPS data exists; notifications delivered | ALL TEAMS

## Windsurf P1 Instructions
P1 HIGH PRIORITY — WINDSURF INSTRUCTIONS (Sprint 1)
ID | Team(s) | Category | Title | Required Change | Files | Consensus
WS-P1-001 | Alpha | Security | Add RBAC to compliance.ts getDashboardStats | Add requireAccess with targetCompanyId to getDashboardStats, getExpiringItems. Filter queries by company. | compliance.ts lines 75-150 | Alpha + Delta
WS-P1-002 | Alpha | Security | Fix dispatch.ts company isolation | getDashboardStats must include targetOwnerId/targetCompanyId checks to prevent cross-company data access. | dispatch.ts line 31 | Alpha + Delta
WS-P1-003 | Alpha | Security | Add RBAC to catalysts.ts | Add requireAccess guards to getStats, getProfile, getInvoices, and all create/update/delete procedures. | catalysts.ts | Alpha
WS-P1-004 | Alpha | Data | Add unique constraint on load_bids(loadId, bidderUserId) | ALTER TABLE load_bids ADD UNIQUE INDEX idx_unique_bid (loadId, bidderUserId) to prevent duplicate bids. | Database migration | Alpha + Epsilon
WS-P1-005 | Epsilon | Financial | Implement Stripe Connect OAuth callback | Create /api/stripe/oauth/callback endpoint. Exchange auth code for Connect ID via stripe.oauth.token(). Store stripeConnectId on user record. | New endpoint + users table | Epsilon + Alpha
WS-P1-006 | Epsilon | Financial | Wire fee deduction into load checkout | In stripe.ts createLoadCheckout: use feeCalculator.calculateFee() to compute platform fee. Set application_fee_amount on checkout session. Record fee in platform_revenue table. | stripe.ts createLoadCheckout procedure | Epsilon
WS-P1-007 | Beta | Frontend | Add factoring sub-routes to App.tsx | Add 9 routes: /factoring/invoices, /catalysts, /collections, /funding, /risk, /aging, /chargebacks, /debtors, /reports. Map to existing FactoringXxx.tsx components with FACT role guard. | frontend/client/src/App.tsx | Beta
WS-P1-008 | Beta | Frontend | Organize role-specific page directories | Move scattered pages into role dirs: /pages/carrier/ (10 pages), /pages/driver/ (10), /pages/broker/ (6), /pages/catalyst/ (6), /pages/escort/ (12), /pages/compliance/ (5), /pages/safety/ (6), /pages/superadmin/ (6). Update import paths in App.tsx. | All page files + App.tsx | Beta
WS-P1-009 | Beta | Frontend | Implement error states across all pages | Add ErrorBoundary wrapper to all major page components. Add error display with retry button (following ShipperLoads.tsx pattern) to all dashboard and list pages. | All dashboard and list page files | Beta
WS-P1-010 | Beta | Frontend | Implement empty states across all pages | Use existing Empty component (components/ui/empty.tsx) in all list pages. Show helpful CTA when no data exists (e.g., 'No loads found — Create your first load'). | All list and dashboard pages | Beta
WS-P1-011 | Delta | Compliance | Validate FMCSA API key on startup | Add health check in server startup: call FMCSA SAFER API with known DOT number. Log warning if key invalid/missing. Set environment variable FMCSA_API_KEY. | Server startup file + .env | Delta + Alpha
WS-P1-012 | Delta | Compliance | Integrate hash-chain for compliance immutability | Wire hash-chain.ts (already exists) into compliance decision logging. Each compliance gate pass/fail gets a hash-chain entry for audit defense. | security/audit/hash-chain.ts + compliance gate code | Delta
WS-P1-013 | Zeta | Real-Time | Implement The Lobby group chat | Create lobby conversation type. Auto-join all company members. Support company-wide announcements. Create 'lobby' channel in WebSocket for real-time broadcast. | messaging.ts + websocket.ts | Zeta + Beta
WS-P1-014 | Gamma | AI | Add secondary LLM fallback for Gemini unavailability | In esangAI.ts: when Gemini API fails after retries, attempt fallback to OpenAI GPT-4o-mini or Anthropic Claude. Add OPENAI_API_KEY or ANTHROPIC_API_KEY env var. Same system prompt. | frontend/server/_core/esangAI.ts + env.ts | Gamma
WS-P1-015 | Epsilon | Financial | Complete accessorial claim → shipper invoice flow | When accessorial claim is approved: 1) Add charge to shipper's next invoice, 2) Record platform facilitation fee (3.5%), 3) Credit carrier wallet. Currently approval updates status but no money moves. | accessorial.ts + billing.ts + wallet.ts | Epsilon + Alpha
WS-P1-016 | Epsilon | Financial | Add refund wallet reconciliation | processRefund() calls Stripe but doesn't update wallet balances. After successful Stripe refund, debit wallet_transactions and update wallet.availableBalance. | payments.ts + wallet.ts | Epsilon
WS-P1-017 | Delta | Compliance | Add document expiration gate before load assignment | Before assigning driver to load: check all required documents (CDL, medical cert, hazmat cert, annual inspection) are uploaded AND not expired. Block assignment if any critical document missing/expired. | dispatch.ts + documentCenter.ts | Delta + Alpha
WS-P1-018 | Zeta | Real-Time | Complete FCM/APNS push notification integration | Push token registry exists but actual FCM/APNS delivery is stubbed. Implement firebase-admin for FCM and @expo/push-notifications for mobile. Wire to notificationService sendPush(). | notificationService.ts + new firebase config | Zeta

## Customer Readiness
CUSTOMER ONBOARDING READINESS — DEPENDENCY MAP
Customer | Role | Workflow | Status | Blocking Issues | Required Windsurf Instructions | ETA After Fixes
AMJ Energy | SHIPPER | Create crude oil loads with ESANG AI | WORKS | Load creation functional; ESANG AI real; hazmat classification works | None (already working) | Ready now
AMJ Energy | SHIPPER | Receive and evaluate carrier bids | BLOCKED | Zero carriers exist to submit bids; no carrier company; no vehicles | WS-P0-011, WS-P0-012, WS-P0-013, WS-P0-015 | After P0 fixes (1 week)
AMJ Energy | SHIPPER | Real-time load tracking | BLOCKED | Zero GPS data; WS events not emitted on lifecycle transitions | WS-P0-007, WS-P0-013, WS-P0-015 | After P0 fixes (1 week)
AMJ Energy | SHIPPER | Process payments via EusoWallet | BLOCKED | No webhooks; no payouts; $0 fees; no settlements | WS-P0-001, WS-P0-002, WS-P0-003, WS-P0-004 | After P0 fixes (1 week)
AMJ Energy | SHIPPER | Compliance documentation | PARTIAL | FMCSA data exists (9.8M records) but API key needs validation; no compliance gates | WS-P0-005, WS-P1-011 | After P0+P1 (2 weeks)
Momentum Crude | SHIPPER/BROKER | Post loads and manage carriers | BLOCKED | Broker has no company; no carrier network; zero carrier companies | WS-P0-011, WS-P0-012, WS-P1-008 | After P0+P1 (2 weeks)
Momentum Crude | SHIPPER/BROKER | Full marketplace and bidding | BLOCKED | Bidding system untested; bid events not emitted; no real-time notifications | WS-P0-008, WS-P0-015 | After P0 fixes (1 week)
Momentum Crude | SHIPPER/BROKER | Track margins and commissions | BLOCKED | Zero fees configured; no settlement data; commission calculation depends on fees | WS-P0-003, WS-P0-004, WS-P1-006 | After P0+P1 (2 weeks)
Blue Wing Midstream | TERMINAL | Appointment scheduling | BLOCKED | Zero appointments; terminal workflows untested; no dock assignment data | WS-P0-015 + new terminal test data | After P0 (1 week)
Blue Wing Midstream | TERMINAL | BOL generation | UNTESTED | BOL router exists but never tested with real load data | WS-P0-015 (end-to-end test) | After P0 (1 week)
Blue Wing Midstream | TERMINAL | Dearman TAS integration | FUTURE | DearmanService.ts exists; integration not live; external dependency | Separate integration project | TBD

## All Findings (53)
COMPLETE FINDINGS REGISTRY — ALL 6 TEAMS
ID | Priority | Team | Category | Finding | Impact | Files
F-001 | P0 | Epsilon | Financial | No Stripe webhook receiver — payments not captured | Money enters but platform has no record | stripe.ts / new webhooks file
F-002 | P0 | Epsilon | Financial | requestPayout() never calls Stripe transfer API | Drivers cannot withdraw money | wallet.ts line ~500
F-003 | P0 | Epsilon | Financial | Zero platform fee configs — $0 revenue | Platform earns nothing | platformFeeConfigs table
F-004 | P0 | Epsilon | Financial | No settlement automation job | Load completion doesn't trigger payment | New cron job needed
F-005 | P0 | Delta | Compliance | No compliance gate at load assignment | Non-compliant carriers can haul loads | dispatch.ts, loadLifecycle.ts
F-006 | P0 | Delta | Compliance | Insurance minimums not enforced at bid accept | Underinsured carriers accepted | loadBidding.ts
F-007 | P0 | Zeta | Real-Time | Load lifecycle transitions don't emit WS events | Clients must poll for updates | loadLifecycle.ts
F-008 | P0 | Zeta | Real-Time | Bid submission doesn't emit WS events | Shippers don't get real-time bid alerts | loadBidding.ts
F-009 | P0 | Alpha | Security | fleet.ts has NO RBAC guards | Multi-tenant isolation broken | fleet.ts
F-010 | P0 | Alpha | Data | 2 orphaned wallet records (userId=0,2) | Payment processing fails | wallets table
F-011 | P0 | Alpha | Data | 5 of 12 user types have no test accounts | Cannot test workflows | users table
F-012 | P0 | Alpha | Data | No carrier company with DOT/MC | Carrier workflows untestable | companies table
F-013 | P0 | Alpha | Data | Zero vehicles registered | Cannot assign equipment to loads | vehicles table
F-014 | P0 | Alpha | Data | Load data integrity issues (lat/lng 0, dates wrong) | Bad data in production | loads table
F-015 | P0 | All | E2E | Zero loads have progressed past 'posted' | Entire platform untested | All files
F-016 | P1 | Alpha | Security | compliance.ts missing company isolation | Cross-company data access | compliance.ts
F-017 | P1 | Alpha | Security | dispatch.ts dashboard stats no company filter | Can view other companies | dispatch.ts
F-018 | P1 | Alpha | Security | catalysts.ts missing RBAC guards | Multi-tenant gap | catalysts.ts
F-019 | P1 | Alpha | Data | No unique constraint on load_bids | Duplicate bids possible | load_bids table
F-020 | P1 | Epsilon | Financial | No Stripe Connect OAuth callback | Carriers can't connect bank | New endpoint
F-021 | P1 | Epsilon | Financial | Fee not wired into checkout | Fees not collected | stripe.ts
F-022 | P1 | Beta | Frontend | Missing factoring sub-routes in App.tsx | 404 on factoring navigation | App.tsx
F-023 | P1 | Beta | Frontend | 8 of 12 role directories empty | Pages scattered in root | pages/*/
F-024 | P1 | Beta | Frontend | Only 1 page has error handling | Broken UI on API failures | All pages
F-025 | P1 | Beta | Frontend | Empty states not implemented | Blank pages confuse users | All list pages
F-026 | P1 | Delta | Compliance | FMCSA API key not validated on startup | Silent failures | Server startup
F-027 | P1 | Delta | Compliance | Hash-chain not integrated for compliance | Weak audit defense | hash-chain.ts
F-028 | P1 | Zeta | Real-Time | The Lobby not implemented | No company-wide chat | messaging.ts
F-029 | P1 | Gamma | AI | No secondary LLM fallback | ESANG down if Gemini down | esangAI.ts
F-030 | P1 | Epsilon | Financial | Accessorial claims don't trigger payment | Approved claims unpaid | accessorial.ts
F-031 | P1 | Epsilon | Financial | Refund doesn't update wallet | Balance mismatch | payments.ts
F-032 | P1 | Delta | Compliance | Document expiration not blocking assignment | Expired docs allowed | dispatch.ts
F-033 | P1 | Zeta | Real-Time | Push notifications stubbed (no FCM/APNS) | Mobile push doesn't work | notificationService.ts
F-034 | P2 | Alpha | Schema | Users table has system metric columns | Schema pollution | users table
F-035 | P2 | Alpha | Performance | Missing indexes on loads.status, users.role | Slow queries | Database
F-036 | P2 | Alpha | Data | Incomplete FK constraints for terminals | Data consistency risk | Schema
F-037 | P2 | Alpha | Backend | Partial router impls (users.ts, fleet.ts) | Missing endpoints | users.ts, fleet.ts
F-038 | P2 | Beta | Frontend | trpc as any bypasses TypeScript safety | Type errors possible | All pages
F-039 | P2 | Gamma | AI | Rate predictions low confidence for sparse lanes | Unreliable predictions | mlEngine.ts
F-040 | P2 | Gamma | AI | RAG context injected without sanitization | Injection risk | esangAI.ts
F-041 | P2 | Delta | Compliance | No pre-trip route compliance warnings shown to drivers | Unaware of permits needed | interstateCompliance.ts
F-042 | P2 | Epsilon | Financial | Factoring: no actual funding execution | Records but no money moves | factoring.ts
F-043 | P2 | Zeta | Real-Time | Typing indicators stubbed | No real-time typing UX | messaging.ts
F-044 | P2 | Zeta | Real-Time | Message search not implemented | Can't find old messages | messaging.ts
F-045 | P2 | Beta | Frontend | Gamification seeded but no real activity data | The Haul feels empty | gamification pages

## Strengths
PLATFORM STRENGTHS — WHAT'S WORKING EXCEPTIONALLY WELL
Team | Area | Rating | Evidence
Alpha | Load Lifecycle Engine | EXCEPTIONAL | 37-state machine with role-based guards, geofence triggers, financial timers, GPS geotags, HOS verification, cargo-aware compliance. 1,399 lines of production-grade state machine.
Alpha | Router Architecture | EXCELLENT | 169 routers, 540+ procedures, all with real DB queries. No TODO/FIXME/STUB markers found. Clean separation of concerns.
Alpha | Database Schema | EXCELLENT | 205 tables, fully normalized, 9.8M FMCSA records pre-loaded. Comprehensive coverage of all 12 user types.
Alpha | RBAC Framework | STRONG | 12-role system with requireAccess guards, ownership filters, audit logging. 32 guard points across critical routers.
Beta | Dashboard Quality | EXCEPTIONAL | Enterprise-grade dashboards: Terminal (688 lines with OPIS/Genscape/Enverus), Wallet (1964 lines with 8 tabs), Compliance (379 lines with 14 doc groups).
Beta | Design System | EXCELLENT | Consistent Jony Ive language: rounded-xl/2xl, glassmorphism, gradient headers (#1473FF→#BE01FF), custom Gilroy font, full light/dark theme.
Beta | Widget System | EXCELLENT | Sophisticated role-specific widget dashboards with customization, drag-and-drop, widget store. Premium analytics widgets.
Beta | Load Creation Wizard | EXCEPTIONAL | 8-step wizard with ESANG AI integration, multi-truck roster, agreement linking, liquid cargo calculations, ERG hazmat lookup.
Gamma | ESANG AI | EXCEPTIONAL | Real Gemini 2.5 Flash integration. 1,776-line AI engine with 418-line system prompt. 30+ whitelisted actions with real DB mutations. Cognitive memory with embeddings.
Gamma | ML Engine | EXCELLENT | 10 independent models: rate prediction, carrier matching, ETA, demand forecast, anomaly detection, bid optimization, churn risk, reliability scoring. Self-trains every 30 min.
Gamma | SPECTRA-MATCH | EXCELLENT | Real Gemini-powered petroleum identification with 165+ crude grades, per-terminal learning loop, rule-based fallback (60-85% confidence offline).
Gamma | Security Posture | STRONG | Prompt injection defense, whitelisted actions only, Zod schema validation, role-based action permissions, audit logging for all AI actions.
Delta | FMCSA Data | EXCEPTIONAL | 9.8M records: 3.1M census, 2.2M authority, 1.8M violations, 1M crashes, 1M insurance. Sub-millisecond indexed queries. Real SAFER API integration.
Delta | Compliance Engine | EXCELLENT | 50+ document types, 50-state matrix, equipment-specific requirements, hazmat classifications, dynamic resolution based on company profile.
Delta | Insurance Monitoring | STRONG | Daily/weekly automated scans, expiration alerts, FMCSA cross-reference, multi-source verification (platform + FMCSA + Canopy Connect).
Epsilon | Wallet Architecture | EXCELLENT | 2,207-line router with real Stripe integration, auto-wallet creation, P2P transfers, cash advances, chat payments, escrow, reconciliation, AI insights.
Epsilon | Fee Calculator | STRONG | Multi-layer logic: base fee + volume discounts + user overrides + promo codes + tiered pricing. Breakdown reporting for transparency.
Epsilon | Accessorial Types | STRONG | 26 accessorial charge types defined with cargo-specific rates, GPS evidence, detention calculation with free time + hourly rates.
Zeta | WebSocket Architecture | EXCELLENT | Native WS with 140+ event types, role-based channels, company isolation, fleet tracking, geofence alerts, GPS broadcasts.
Zeta | GPS/Geofencing | EXCELLENT | 30-second tracking, circle/polygon geofences, automatic state transitions, driver behavior scoring (speeding, harsh braking/acceleration).
Zeta | Notification System | STRONG | Multi-channel (WS, push, email, SMS), per-user preferences, quiet hours, priority escalation, 4 urgency levels.