## Executive Summary
EusoTrip Gold Standard Audit — Comprehensive Platform Review
Generated: March 05, 2026 ¦ 6 Teams ¦ 160+ Routers ¦ 300+ Pages ¦ 206 DB Tables
PLATFORM HEALTH SCORECARD
System | Team | Status | Score | Blockers | Notes
Backend Architecture | Alpha | NEEDS CLEANUP | 65% | 15 | 160+ routers. 15 stubs returning []. 14 redundant pairs. Shared utilities duplicated across 40+ files.
Frontend UX | Beta | NEEDS CLEANUP | 60% | 13 | 300+ pages. 13+ duplicate pages (4 load creators, 4 fleet, 3 audit logs, 3 news feeds). Menu imbalance: Dispatch 14 items vs Terminal 26.
AI / ML Engine | Gamma | PRODUCTION-READY | 92% | 0 | Real Gemini 2.5 Flash. 10 ML models trained on live data. SPECTRA-MATCH 130+ grades. Visual Intelligence. Self-hosted embeddings.
Compliance & Regulatory | Delta | FUNCTIONAL w/ GAPS | 78% | 3 | FMCSA 14 tables (714K records). All 9 hazmat classes. ERG 1,980 materials. GAPS: No CDL verification router, HOS cert stubbed, insurance 0 active policies.
Financial Systems | Epsilon | FUNCTIONAL w/ GAPS | 72% | 5 | Wallet 2,258 lines + Stripe Connect. Real settlements. Factoring. GAPS: No idempotency, no settlement PDF, disputes stub, no escrow hold, no accessorial deadline.
Real-time / WebSocket | Zeta | PARTIAL | 55% | 4 | 140 events DEFINED but emission chain incomplete. GPS tables exist but no real-time transmission. Gamification wired (30+ locations). Notifications DB+email working.
Dispatch Module | All | COMPLETE | 100% | 0 | 22/22 verified. Command Center, Kanban, 6 components, 4 new endpoints, 6 DB tables, Google Maps, check-call scheduler.
CRITICAL BLOCKERS (Must Fix Before Customer Demos)
# | Blocker | Team | Severity | Impact | Fix
1 | No Account Closure / Deactivation | Alpha | P0 | Users cannot close accounts. Violates GDPR/CCPA. No way to remove non-compliant carriers. | Add users.closeAccount(), users.deactivateAccount() with cascade deletion + audit trail
2 | No Password Reset Flow | Alpha | P0 | Users locked out permanently. Drivers cannot operate. Operational shutdown risk. | Add security.resetPassword() with email verification tokens
3 | No 2FA / MFA for Any Role | Alpha | P0 | Single password compromise = unauthorized hazmat shipments. FMCSA penalty risk. | Add security.setupMFA(), security.verifyMFA() with TOTP support
4 | No Financial Idempotency Keys | Epsilon | P0 | Network retry = double payment. Affects all wallet mutations, settlements, escrow. | Add idempotency key parameter to all financial mutations
5 | Settlement Docs Not Persisted | Epsilon | P0 | No PDF generation, no S3 storage. Legal audit will fail. | Add settlement PDF generation + cloud storage
6 | Dispute Resolution is Stub | Epsilon | P0 | approveSettlement() and resolveDispute() are no-ops. Cannot handle chargebacks. | Implement mediation queue, escrow holds, escalation workflow
7 | No CDL Verification Router | Delta | P0 | Drivers assigned hazmat loads without verified CDL. 49 CFR 391.41 violation. | Create CDL verification router with FMCSA SAFER API lookup
8 | GPS Not Transmitted Real-time | Zeta | P0 | GPS tables exist, events defined, but emitGPSUpdate() never called. Dispatchers blind. | Wire emitGPSUpdate() in location/tracking routers on every position update
9 | Insurance: 0 Active Policies in DB | Delta | P1 | insurancePolicies table exists but 0 records. Platform technically running uninsured. | Populate via carrier onboarding or third-party API verification
10 | No Escrow Hold Before Settlement | Epsilon | P1 | Carrier wallet credited IMMEDIATELY on delivery. Shipper can dispute after funds released. | Add 72-hour escrow hold before auto-release
11 | WebSocket Emission Chain Broken | Zeta | P1 | emitLoadEvent/emitBidEvent defined but router layer never calls them. | Wire emission calls into loads.ts, loadBidding.ts, loadLifecycle.ts
12 | HOS Log Certification Stubbed | Delta | P1 | Certification returns mock data, not persisted. 49 CFR 395 compliance gap. | Persist certified logs with driver signature to database

## Redundancies
Redundancy Audit — Backend Routers + Frontend Pages
BACKEND: 15 STUB ROUTERS TO DELETE
# | Router File | Lines | What It Returns | Action
1 | catalystPackets.ts | 21 | list()→[], getSummary()→{total:0,...} | DELETE — no DB queries
2 | shipperContracts.ts | 42 | list()→[], getSummary()→zeros, getById()→stub obj | DELETE — use contracts.ts
3 | rateConfirmations.ts | 25 | list()→[], getById()→hardcoded stub | DELETE — implement in loadBidding.ts
4 | mileage.ts | 20 | calculate()→{miles:0,...}, getRecent()→[] | DELETE — use location.ts calculateETA
5 | tolls.ts | 41 | getRecentRoutes()→[], calculate()→{tollCost:0,...} | DELETE — implement in routes.ts
6 | fuelCards.ts | 34 | list()→[], getRecentTransactions()→[] | DELETE — needs fuel_cards table first
7 | help.ts | 18 | getCategories()→[], getArticles()→[] | DELETE — implement in support.ts
8 | traffic.ts | 38 | getIncidents()→[], getConstruction()→[], getDelays()→zeros | DELETE — use weather.ts or routes.ts
9 | routing.ts | 46 | calculateRoute()→{distance:0,...}, getSavedRoutes()→[] | DELETE — duplicate of routes.ts
10 | procedures.ts | 16 | getAll()→[], getChecklists()→[] | DELETE — implement in training.ts
11 | newsfeed.ts | 151 | getFeed()→hardcoded empty, getFeatured()→[] | DELETE — use news.ts
12 | facility.ts | 46 | getBays()→[], getStaff()→[] | DELETE — use facilities.ts
13 | features.ts | 47 | list()→[] | DELETE — implement in settings.ts
14 | feedback.ts | 20 | list()→[] | DELETE — implement in support.ts
15 | exports.ts | 33 | list()→[], getTemplates()→[] | DELETE — implement in reports.ts
BACKEND: 8 REDUNDANT ROUTER PAIRS TO CONSOLIDATE
# | Keep | Delete/Merge | Reason
1 | messages.ts (1,327 lines) | messaging.ts (429 lines) | messages.ts has full OpenIM arch: conversations, receipts, typing, search. messaging.ts is simpler duplicate.
2 | vehicles.ts (389 lines) | vehicle.ts (162 lines) | vehicles.ts has full fleet mgmt. vehicle.ts is inspection-only subset. Merge inspection into vehicles.
3 | facilities.ts (199 lines) | facility.ts (46 lines) | facility.ts is pure stub. facilities.ts has real search/filter/pagination.
4 | documentCenter.ts (1,769 lines) | documents.ts (496 lines) | documentCenter.ts has smart doc mgmt, compliance tracking, 50-state matrix. documents.ts is basic listing.
5 | news.ts (188 lines) | newsfeed.ts (151 lines) | news.ts has real RSS API. newsfeed.ts returns hardcoded empty array.
6 | dispatch.ts (1,426 lines) | dispatchRole.ts (628 lines) | dispatch.ts is complete command center. dispatchRole.ts is simpler role-specific subset. Merge with role filter.
7 | alerts.ts + notifications.ts | Consolidate into notifications.ts | Three-way overlap. alerts.ts=severity-based, notifications.ts=categories, push.ts=device tokens. Keep push.ts for devices.
8 | loads.ts (2,651 lines) | Consider migrating to loadBoard.ts | loadBoard.ts is marked 'gold standard'. loads.ts appears legacy. Needs architectural review.
FRONTEND: 13+ DUPLICATE PAGES TO CONSOLIDATE
# | Category | Keep (Canonical) | Archive/Delete | Impact
1 | Load Creation (4!) | shipper/CreateLoad.tsx (672 lines, 7-step) | LoadCreate.tsx (765), CreateLoad.tsx (218), LoadCreationWizard.tsx (2,654) | Users don't know which wizard to use. /loads/create route ambiguous.
2 | Fleet Views (4!) | FleetOverview.tsx (413 lines, richest) | Fleet.tsx (194), FleetManagement.tsx (184), FleetCommandCenter.tsx (218) | 4 fleet pages with overlapping data. Catalyst confusion.
3 | Audit Logs (3!) | AuditLogs.tsx (142 lines, full-featured) | AuditLog.tsx (68, detail view), AuditLogsPage.tsx (120, duplicate) | Bug fix = 3 places. Keep Audits.tsx (276) for compliance officer.
4 | News Feeds (3!) | NewsFeed.tsx (457 lines, cache polling) | LiveNewsFeed.tsx (330), NewsfeedPage.tsx (149) | Dead code. Only one mounted in routes.
5 | Messaging (2) | Messages.tsx (932 lines, full-featured) | MessagingCenter.tsx (601, subset) | Both in menus. Users get random version.
6 | DVIR/Inspect (3) | DVIR.tsx (275, driver) + DVIRManagement.tsx (134, admin) | VehicleInspections.tsx (236), PreTripInspection.tsx (179) | Drivers have 3 inspection pages. Which is correct?
7 | Notifications (2) | NotificationCenter.tsx (273) | NotificationsCenter.tsx (11, pure redirect) | Already aliased. Delete the alias file.
8 | SpectraMatch (!) | SpectraMatch.tsx | SpectraMatch 2.tsx (SPACE IN FILENAME) | Build system nightmare. Most bundlers choke on spaces.

## Role UX Gaps
Role-by-Role UX Completeness — 'Can This Person Do Their Job?'
Role | Menu Items | Journey Complete? | Critical Gap | What's Missing | Ryan Davis Test
DISPATCHER | 14 items | 50% | SEVERELY UNDER-SERVED | No 'Pay Drivers' from dispatch. No 'Broadcast Message' quick action. No 'Bulk Load Import'. No ELD Intelligence. 46% fewer menu items than Terminal. | 'Creates additional work' — forced to navigate away for EVERY payment, message, and ELD check.
SHIPPER | 23 items | 60% | Can't pay from POD view | No 1-click 'Pay Driver' from POD. BidManagement not in menu. RecurringLoadScheduler not wired. 4 different load creation pages. | 'Resolves nothing' — posts load fine, but payment requires 3+ navigation clicks.
DRIVER | 24 items | 70% | Status updates buried | No prominent 'Mark Delivered' button. Must open CurrentJob, scroll, find button. HOSCompliance not in menu. Pre-trip inspection duplicated 3 ways. | Would say 'where do I click?' for the most critical daily action.
CARRIER (Catalyst) | 24 items | 75% | Fleet page confusion | 4 different fleet pages. RateNegotiations not wired. No bulk bid submission. | Would say 'which fleet page do I use?' and never find rate negotiation.
BROKER | 24 items | 75% | No 'my posted loads' hub | No unified view of posted loads with action buttons. Settlement scattered across 3 pages. | Would say 'where are my loads?' — no single command center.
TERMINAL MANAGER | 26 items | 80% | Best-served role | Minor: TerminalCreateLoad not in menu. Otherwise complete: appointments, gate, dock, SCADA. | Would say 'this actually works for me.'
ESCORT | 21 items | 70% | No real-time convoy tracking | WebSocket convoy events defined but not transmitted. No live position sharing. | Would say 'I can't see where the truck is.'
FACTORING | 17 items | 75% | Dispute stub | Factoring dashboard complete. BUT dispute resolution is a no-op. Collections incomplete. | Would say 'what happens when someone disputes?'
COMPLIANCE | 23 items | 78% | CDL verification missing | No CDL verification router. FMCSA lookup not linked from dashboard. Insurance shows 0 active. | Would say 'I can't verify a single CDL.'
SAFETY MANAGER | 21 items | 75% | HOS cert stubbed | HOS log certification returns mock data. Safety alerts WebSocket not transmitting. | Would say 'I can't certify any logs.'
ADMIN | 18 items | 65% | No account management | No close/deactivate/suspend user. No role permissions editor. Feature flags empty. | Would say 'I can't remove a bad actor.'
SUPER ADMIN | 21 items | 70% | No 2FA enforcement | Cannot enforce 2FA. No session management. Platform fees work but no fee change audit trail. | Would say 'anyone can hack any account.'

## AI Systems
AI / ML Systems Inventory — What's Real
System | File | Lines/Size | Status | Technology | Evidence
ESANG AI (Chat) | _core/esangAI.ts | 1,838 | REAL | Gemini 2.5 Flash API | Direct API calls, retry logic, 30s timeout, safety settings, conversation history, 25 registered actions
ML Engine (10 models) | services/mlEngine.ts | 1,536 | REAL | Self-trained from DB | Rate prediction, carrier matching, ETA, demand forecast, anomaly detection, dynamic pricing, reliability, churn, bundling, bid optimizer
SPECTRA-MATCH | routers/spectraMatch.ts | 665 | REAL | Static DB + Gemini | 130+ crude grades, 12 parameters, tolerance scoring, AI fusion with Gemini for ambiguous matches
Visual Intelligence | services/visualIntelligence.ts | 595 | REAL | Gemini Vision API | 9 analysis types: mechanical diagnosis, gauge reading, seal verification, DVIR, cargo, POD, facility, damage, road condition
Embeddings/RAG | services/embeddings/ | 344 | REAL | Self-hosted TEI | Azure Container Instance, pplx-embed-v1-0.6b, 1024-dim, LRU cache, cosine similarity search
NLP Processor | services/ai/nlpProcessor.ts | 24 KB | REAL | Intent/Entity/Sentiment | Intent detection, entity extraction, sentiment analysis. Non-blocking, graceful fallback.
Fraud Scorer | services/ai/fraudScorer.ts | 19 KB | PARTIAL | Rule-based + ML | Exists but NOT integrated into main transaction flows. Needs wiring.
Gamification | routers/gamification.ts | 1,575 | REAL | Event-driven | 24 event types, 30+ wired locations, mission system, badge/XP, leaderboards, crate rewards
Market Intelligence | routers/marketIntelligence.ts | 275 | REAL | ML + external data | Theft risk, emissions, resilience, driver wellness, tariff impact
Equipment Intelligence | routers/equipmentIntelligence.ts | 748 | REAL | Catalog + Gemini | 100+ equipment types, AI match scoring, load compatibility analysis
Facility Intelligence | routers/facilityIntelligence.ts | 823 | REAL | DTN + DB | Facility search, nearby discovery, DTN sync, detention GPS, portfolio analysis
Zeun Mechanics | services/zeunMechanics.ts | 99 KB | REAL | Gemini Vision | Multi-pass mechanical diagnosis, repair estimation, provider matching

## Financial Gaps
Financial Systems — Gaps & Risks
# | Gap | Current State | Risk | Required Fix | Severity
1 | No Idempotency Keys | Zero matches for 'idempotency' in codebase | Network retry = double payment on releaseEscrow, transferP2p, requestCashAdvance | Add idempotency key param to all financial mutations with dedup check | P0
2 | Settlement Docs Not Persisted | Records in DB but never exported to PDF/S3 | Legal audit failure. No proof of settlement terms. | Generate PDF on settlement creation, store in cloud | P0
3 | Dispute Resolution Stub | approveSettlement() returns {success:true} without DB update. resolveDispute() is no-op | Cannot handle chargebacks. No mediation. No escalation. | Build mediation queue, escrow holds, admin escalation workflow | P0
4 | No Escrow Hold | Carrier wallet credited IMMEDIATELY on delivery | Shipper disputes after funds released = platform liability | 72-hour escrow hold before auto-release. Hold on dispute. | P1
5 | No Accessorial Deadline | Claims accepted ANYTIME after delivery | Carrier submits detention claim 6 months later. No cutoff. | Enforce 30-day submission deadline. Validate GPS against facility. | P1
6 | Stripe Webhook Signature | No evidence of webhook signature validation | Man-in-middle can forge payment confirmations | Add Stripe webhook signature verification (stripe.webhooks.constructEvent) | P1
7 | No Configurable Payout Schedule | All payouts immediate (no net-30/net-15 option) | Carriers expect flexible payout terms | Add configurable payout schedules per carrier profile | P2
8 | No Batch Reconciliation | No scheduled Stripe API reconciliation | Stripe balance ≠ platform balance over time | Add nightly batch reconciliation job against Stripe API | P2

## Compliance Gaps
Regulatory Compliance Gaps — FMCSA / DOT / Insurance
# | Gap | Regulation | Current State | Risk | Fix
1 | No CDL Verification Router | 49 CFR 391.41 | Zero matches for CDL verification in routers | Drivers assigned hazmat without verified CDL. FMCSA penalty. | Create CDL router with SAFER API lookup
2 | Insurance: 0 Active Policies | 49 CFR 387 | insurancePolicies table exists, 0 records | Platform running technically uninsured | Populate via onboarding + 3rd party API
3 | HOS Cert Stubbed | 49 CFR 395 | Certification returns mock data, not persisted | Non-compliant ELD logs | Persist certified logs with driver signature
4 | GPS Not Real-time | 49 CFR 392 | Tables + events defined but never transmitted | No live tracking for dispatchers/safety | Wire emitGPSUpdate() on every position update
5 | No Hazmat Endorsement Blocking | 49 CFR 383.93 | System checks endorsement but doesn't block assignment | Unendorsed driver can be assigned hazmat | Add hard gate in assignDriver mutation
6 | No TWIC Card Expiry Alerts | 49 CFR 1572 | TWIC field exists but no expiry monitoring | Expired TWIC = denied facility access | Add 30-day expiry alerts in compliance events
7 | No Accident Reporting (DOT 5800) | 49 CFR 390.15 | DOT5800Form page exists but backend stub | No official accident form submission | Wire to FMCSA reporting API

## Real-time Gaps
WebSocket & Real-time Event Audit — 140+ Events
Event Category | Events Defined | Emission Functions | Actually Emitted? | Gap
LOAD_EVENTS (15) | 15 | emitLoadEvent() | PARTIAL | Events defined and function exists but NOT called from loads.ts router layer
BID_EVENTS (10) | 10 | emitBidEvent() | PARTIAL | emitBidAwarded() found. Other bid events may not fire from loadBidding.ts
DRIVER_EVENTS (15) | 15 | emitDriverStatusChange() | PARTIAL | Status change emitter exists. hos_warning/violation events NOT wired to HOS engine
VEHICLE_EVENTS (12) | 12 | emitVehicleEvent() | PARTIAL | Function exists. telemetry_update never called. breakdown/maintenance NOT wired to Zeun
MESSAGE_EVENTS (10) | 10 | WebSocket native | YES | Messages use native WebSocket. Fully functional.
NOTIFICATION_EVENTS (8) | 8 | emitNotification() | YES | Working. DB + email/SMS notifications functional.
GAMIFICATION_EVENTS (12) | 12 | emitGamificationEvent() | YES | 30+ wired locations. fireGamificationEvent() called throughout platform.
COMPLIANCE_EVENTS (10) | 10 | emitComplianceAlert() | PARTIAL | Function exists. NOT called from compliance/insurance routers.
SAFETY_EVENTS (12) | 12 | emitSafetyIncident() | PARTIAL | Function exists. NOT called from safety.ts or safetyAlerts.ts.
DISPATCH_EVENTS (10) | 10 | emitDispatchEvent() | YES | FULLY WIRED after overhaul. BOARD_UPDATE (2 points), CHECK_CALL_DUE (scheduler).
TERMINAL_EVENTS (10) | 10 | emitTerminalEvent() | PARTIAL | Function exists. NOT called from terminals.ts.
ESCORT_EVENTS (8) | 8 | emitEscortEvent() | PARTIAL | Function may exist. convoy_formed/update NOT wired to escorts.ts.
FINANCIAL_EVENTS (12) | 12 | emitFinancialEvent() | PARTIAL | Function exists. NOT called from wallet.ts or loadLifecycle.ts settlements.
TRACKING_EVENTS (8) | 8 | emitGPSUpdate() MISSING | NO | CRITICAL: No GPS emission function. 8 tracking events NEVER fire. Dispatchers are blind.
ZEUN_EVENTS (8) | 8 | emitZeunEvent() | PARTIAL | Function exists. NOT called from zeunMechanics.ts.
EMERGENCY_EVENTS (10) | 10 | emitEmergencyEvent() | PARTIAL | Function exists. NOT called from emergencyResponse.ts.
SYSTEM_EVENTS (10) | 10 | Native WebSocket | YES | Connection lifecycle events work natively.

## Windsurf Instructions
Prioritized Windsurf Instructions — Gold Standard Roadmap
P0 = Before customer demos ¦ P1 = Within 2 weeks ¦ P2 = Within 1 month ¦ P3 = Polish
# | Priority | Instruction | Team | Files | Est Hours | Verification
1 | P0 | Implement account closure: users.closeAccount() with cascade deletion, data retention policy, audit trail | Alpha | users.ts, schema.ts | 8 | search_code 'closeAccount' in users.ts
2 | P0 | Implement password reset: security.resetPassword() with email verification tokens, expiry, rate limiting | Alpha | security.ts or users.ts, email service | 6 | search_code 'resetPassword'
3 | P0 | Implement 2FA/MFA: security.setupMFA(), verifyMFA() with TOTP (speakeasy or otplib) | Alpha | security.ts, schema.ts (mfa_secrets table) | 8 | search_code 'setupMFA' + SQL for mfa table
4 | P0 | Add idempotency keys to ALL financial mutations: wallet transfers, escrow release, settlements | Epsilon | wallet.ts, loadLifecycle.ts, schema.ts | 6 | search_code 'idempotency' — expect 10+ matches
5 | P0 | Generate settlement PDFs + store in S3/Azure Blob on every settlement creation | Epsilon | loadLifecycle.ts, new: settlementPDF.ts | 8 | search_code 'settlementPdf' or 'generatePDF'
6 | P0 | Implement dispute resolution: mediation queue, escrow hold on dispute, admin escalation | Epsilon | earnings.ts, admin.ts, wallet.ts | 10 | search_code 'resolveDispute' — must have DB update
7 | P0 | Create CDL verification router: FMCSA SAFER API lookup, endorsement validation, expiry tracking | Delta | NEW: cdlVerification.ts, schema.ts | 8 | search_code 'cdlVerification' + SQL for cdl table
8 | P0 | Wire GPS real-time transmission: emitGPSUpdate() called in location.ts on every position update | Zeta | location.ts, tracking.ts, websocket.ts | 6 | search_code 'emitGPSUpdate' in server — expect 3+ calls
9 | P1 | Add 72-hour escrow hold: auto-release after hold period unless disputed | Epsilon | loadLifecycle.ts, scheduler.ts | 6 | search_code 'escrowHold' or 'autoRelease'
10 | P1 | Enforce 30-day accessorial submission deadline, validate GPS against facility geofence | Epsilon | accessorial.ts, geofencing.ts | 4 | read_file accessorial.ts — must check date
11 | P1 | Populate insurance policies via onboarding or 3rd party API verification | Delta | insurance.ts, onboarding.ts | 6 | SQL: SELECT COUNT(*) FROM insurancePolicies — expect > 0
12 | P1 | Persist HOS log certification with driver signature (not mock data) | Delta | hos.ts, schema.ts | 4 | read_file hos.ts — certification must write to DB
13 | P1 | Add hazmat endorsement hard gate in assignDriver — block if not endorsed | Delta | dispatch.ts (assignDriver mutation) | 3 | search_code 'endorsement' in dispatch.ts — must have TRPCError throw
14 | P1 | Wire emitLoadEvent() calls in loads.ts and loadLifecycle.ts on status changes | Zeta | loads.ts, loadLifecycle.ts | 4 | search_code 'emitLoadEvent' in server — expect 5+ calls
15 | P1 | Wire emitBidEvent() calls in loadBidding.ts on bid submit/accept/counter | Zeta | loadBidding.ts | 3 | search_code 'emitBidEvent' — expect 4+ calls
16 | P1 | Wire emitFinancialEvent() in wallet.ts on transfers, deposits, withdrawals | Zeta | wallet.ts | 3 | search_code 'emitFinancialEvent' — expect 6+ calls
17 | P1 | Delete 15 stub routers (catalystPackets, shipperContracts, rateConfirmations, mileage, tolls, fuelCards, help, traffic, routing, procedures, newsfeed, facility, features, feedback, exports) | Alpha | 15 router files | 2 | list_directory server/routers — 15 fewer files
18 | P1 | Consolidate messaging.ts into messages.ts, vehicle.ts into vehicles.ts, documents.ts into documentCenter.ts | Alpha | 3 pairs of files | 4 | search_code 'messaging' — only in messages.ts
19 | P1 | Consolidate 4 load creators → shipper/CreateLoad.tsx. Archive LoadCreate, CreateLoad, LoadCreationWizard. | Beta | 4 page files + App.tsx routing | 4 | Route /loads/create → shipper/CreateLoad.tsx only
20 | P1 | Fix SpectraMatch 2.tsx filename (remove space) | Beta | Rename file | 0.5 | list_directory pages — no spaces in filenames
21 | P1 | Add to DISPATCH menu: Pay Drivers, Broadcast Message, Recurring Lanes, ELD Intelligence, HOSCompliance | Beta | menuConfig.ts | 3 | read_file menuConfig.ts DISPATCH section — expect 20+ items
22 | P1 | Wire orphaned pages into menus: BidManagement→SHIPPER, HOSCompliance→DRIVER+DISPATCH, RecurringLoadScheduler→SHIPPER | Beta | menuConfig.ts | 2 | search_code 'BidManagement' in menuConfig.ts
23 | P2 | Extract resolveUserId() into shared utility (duplicated across 40+ routers) | Alpha | NEW: utils/resolveUser.ts + 40 routers | 8 | search_code 'resolveUserId' — expect 1 definition
24 | P2 | Consolidate 4 fleet pages → FleetOverview.tsx | Beta | 4 page files + App.tsx | 3 | Route /fleet → FleetOverview.tsx only
25 | P2 | Consolidate 3 news feeds → NewsFeed.tsx | Beta | 3 page files + App.tsx | 2 | Route /news → NewsFeed.tsx only
26 | P2 | Wire remaining WebSocket events: safety, compliance, terminal, escort, zeun, emergency | Zeta | 6+ router files | 12 | search_code 'emitSafetyIncident' in safety.ts
27 | P2 | Integrate fraudScorer.ts into wallet.ts transaction flows | Gamma | wallet.ts, fraudScorer.ts | 6 | search_code 'fraudScore' in wallet.ts
28 | P2 | Implement Stripe webhook signature validation | Epsilon | stripe.ts | 2 | search_code 'constructEvent' in stripe.ts
29 | P3 | Archive 13 duplicate frontend pages (per Redundancies sheet) | Beta | 13 page files | 3 | list_directory pages — 13 fewer files
30 | P3 | Add batch Stripe reconciliation nightly job | Epsilon | NEW: jobs/stripeReconciliation.ts | 6 | search_code 'stripeReconciliation'
31 | P3 | Upgrade demand forecasting from linear trend to Prophet/ARIMA | Gamma | mlEngine.ts | 8 | search_code 'prophet\¦arima' in mlEngine.ts
32 | P3 | Add configurable payout schedules (net-15, net-30) | Epsilon | wallet.ts, schema.ts | 6 | search_code 'payoutSchedule'
P0: 8 items (~60h) ¦ P1: 14 items (~48h) ¦ P2: 6 items (~33h) ¦ P3: 4 items (~23h) ¦ TOTAL: 32 items (~164h)